## PPM Tracker
Aparna Property Management Services Pvt Ltd
S.no | Site Name | Asset Description | Capacity/Qty | Location | Date of Schudle | Date of Completion | Delay Days | Reason for Delay | Remarks
1 | Aparna Sarovar | DG Sets | 250 KVA - 16 Nos | All block PCCrooms | 4th Week | 29.12.2018 | Nil | Nil
2 |  | VCB | 800 amps 13 No | All block Transformer yards & 3 panel , 5 panel | 4th Week | 28.12.2018 | Nil | Approval pending from ASOWS | PPM done for 1 NO VCB during power failure
3 |  | Solar Fencing | 1132 m / 4 Zones | Main gate(Total site surrounding) | 4th Week | - | 3 | Technician was not available | Technician will attend 1st week of Jan 19
4 |  | Common supply panels 7 No's | - | Podium | 2nd Week | 10.12.2018 | Nil | Nil
|  | Irrgation starters 14 No's | - | All blocks fire Pump rooms | 3rdWeek | 17.12.2018 | Nil | Nil
|  | Water body starters 05 No's | - | WSP | 4th Week | 21.12.2018 | Nil | Nil
|  | STP Panel 2 No's | - | STP | 2nd Week | 12.12.2018 | Nil | Nil
5 |  | WSP Panel 1 No | - | WSP | 2nd Week | 12.12.2018 | Nil | Nil
6 |  | STP -Hydro pneumatic pumps | 25 HP/ 4 No's | STP | 4th Week | 31.12.2018 | Nil | Nil
7 |  | WSP -Hydro pneumatic pumps | 30 HP/ 4 No's | STP | 3rd Week | 31.12.2018 | Nil | Nil
8 |  | STP feed pump | 2 HP/ 2 No's | STP | 3rd Week | 25.12.2018 | Nil | Nil
9 |  | STP- Air Blowers - 3 No's | 30 HP/ 3 No's | STP | 3rd Week | 25.12.2018 | Nil | Nil
10 |  | Jockey Pumps - 14 No's | 7.5HP/14 No's | All block Fire pump rooms | 3rd Week | 31.12.2018 | Nil | Nil
11 |  | STP Final tank | 500KL 1 No | STP | 1st Week | - | 2 | planned in Jan19
12 |  | Garden area chambers | - | At blocks & Podium | 4th Week | 27.12.2018 | Nil | Nil