## Sheet1
Site | Category | Observation | Location
95 | 8 | Patch works to be done | 14 th Floor Service stair case
95 | 7 | Drain jally yet to provided at corridor | 1408 flat
95 | 8 | Lowers to be provided for plumbing duct doors at 3rd & 4th Flats side | 13 th floor
95 | 1 | Hanging 2' light to be fixed properly | 11 th floor Service Staircase
95 | 8 | Lowers to be provided for plumbing duct doors at at 4 th flat | 10 th floor
95 | 8 | Lowers to be provided for plumbing duct doors at 3 rd flat | 9 th floor
95 | 8 | Lowers to be provided for plumbing duct doors at 1 st flat | 9 th floor
95 | 8 | Gaps to be filled properly near 4 th flat fire duct. | 9 th floor
95 | 8 | Lowers to be provided for plumbing duct doors at 1 st flat | 8 th floor
95 | 8 | Lowers to be provided for plumbing duct doors at 4 th flat | 7 th floor
95 | 8 | Missing of one no. sliding UPVC window at corridor near 502 flat | 5 th floor
95 | 8 | Missing of one no. sliding UPVC window at corridor near 402 flat | 4 th floor
95 | 8 | UPVC window yet to be provided at corridor near 402 flat | 4 th floor
95 | 8 | 8 th flat plumbing duct aluminium lowers not provided. | 4 th floor
95 | 8 | 8 th flat plumbing duct aluminium lowers not provided. | 3 rd floor
95 | 8 | Unwanted holes to be filled | 3 rd floor service staircase
95 | 7 | Drain jally yet to provided at corridor | 2 nd floor
95 | 8 | Double hight floor deep cleaning and proper drain to be provided between 5 and 6 flats. | 2 nd floor
95 | 8 | Unwanted holes to be closed | 2 nd floor
95 | 8 | Satircase steps damaged. | Ground floor service staircase
95 | 8 | Open to sky area deep cleaning and drain jolly to provided near G02 flat. | Ground floor
95 | 8 | 3 rd flat plumbing duct aluminium lowers not provided. | Ground floor
95 | 8 | Upvc window/M.S grill missing. | Basement-1 service stair
95 | 8 | Upvc window/M.S grill missing. | Basement-2 service stair
95 | 8 | Grills to be provided for all corridor windows. | All Corridors
95 | 8 | All electrical,communication and fire duct doors deep cleaning to be done. | All Corridors
95 | 8 | All MCP's Deep cleaning & PA speaker covers to be removed. | All Corridors
95 | 8 | Corridor deep cleaning, paint marks and dead mortors to be removed. | All Corridors
95 | 8 | External fasade deep cleaning and dead mortors to be removed. | All Corridors
95 | 8 | Debris need to be remove from corridor. | All Corridors
95 | 8 | Patch work pending infornt of P1,P2 And Service lifts. | All Corridors
95 | 8 | Upvc windows glass Internal & external cleaning and stickers to be removed. | All Corridors
95 | 8 | Hand rails painting need to be done. | All Staircases.
95 | 8 | Corridor final coat paint pending. | All Corridors
95 | 8 | Corridor and Staircase light paint marks cleaning. | All corridors & All staircase
95 | 8 | Floor Signage missing at corridors and staircases. | All corridors & All staircase
95 | 8 | STP Exaust duct door Corners damaged. | 14,13,12,11,10 th Corridors
95 | 8 | Corridor fire extinguishers deep cleaning to be done. | All Corridors
95 | 8 | Corridor tile skutting deep cleaning to be done. | All Corridors