## Handing over
Aparna Sarovar Grande
List Of Equipment/Assets - Handing Over - Taking Over Documents Report
S.No | Location | Type Equipment | Catogery | Vendor | Commissioning Details | WO | PO | BOQ | Manual | Drawings | Warranty Details | Vendor Contacts | Pending DOC'S | Project Handover Coordinator | Taken Over By | Status | Remarks
1 | A-block Basement-2 | STP | Electrical& Electro Mechanical | Revolve Engineers | 2016-05-01 | Yes | Yes | Yes | Yes | Yes | May-16 to April-18 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Revolve-Vijay | N.Rama Krishnamraju |  | Centrifuge Commissioning not completed
2 | A-block Basement-2 | Hydro-Pneumatic system for STP | Electrical& Electro Mechanical | Revolve Engineers | 2016-06-01 | Yes | Yes | Yes | Yes | NO | june-2016 to june-2017 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Revolve-Suresh | N.Rama Krishnamraju
3 | A-block Basement-2 | Hydro-Pneumatic system for Metro water supply | Electrical& Electro Mechanical | Revolve Engineers | 2015-09-15 | Yes | Yes | Yes | Yes | NO | sep-15 to aug-16 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Revolve-Suresh | N.Rama Krishnamraju
4 | A-block Basement-2 | Hydro-Pneumatic system for Domestic water supply | Electrical& Electro Mechanical | Revolve Engineers | 2015-09-15 | Yes | Yes | Yes | Yes | NO | sep-15 to aug-16 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Revolve-Suresh | N.Rama Krishnamraju
5 | A-block Basement-2 | Softening Plant | Mechanical | Coron India | 2015-11-28 | Yes | Yes | Yes | Yes | Yes | 28-11-2015 to 27-11-2016 | NO.231,SRIRAM, 1ST FLOOR, 5TH AIN, JRD TATA NAGAR, KODIGEHALLI, BANGALORE-560092 | No | Kamal | N.Rama Krishnamraju
|  | Pump's | Electrical& Electro Mechanical | Revolve Engineers | 2015-11-28 | Yes | Yes | Yes | Yes | NO | 28-11-2015 to 27-11-2016 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Revolve-Suresh | N.Rama Krishnamraju
6 | Basement-2 | Fire & Safety (A to D) | Mechanical | Sujay | 2015-11-20 | Yes | Yes | Yes | Yes | Yes | 20-11-15 to19-11-16 | 5-9-286/2/75, Plot No.75, Rajeevgandi Nagar, Prasanthi Nagar extn, I.E Kukatpally, Hyd-500072 | No | Naresh | Naveen prasad & N.Rama Krishnamraju
7 | Basement-2 | Fire & Safety (E to I) | Mechanical | Decars | 2016-08-08 | Yes | Yes | Yes | Yes | Yes | 08-08-2016 to 07-08-2017 | 1-10-212/2, St No:6, ASHOK NAGAR, HYD-500020 | No | M.Praveen Kumar | Naveen prasad & N.Rama Krishnamraju
8 | Basement-2 | Fire Jockey, Main&DG Pumps | Electro Mechanical | Revolve Engineers | 2015-11-20 | Yes | Yes | Yes | Yes | Yes | 20-11-15 to19-11-16 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Mahesh | Naveen prasad & N.Rama Krishnamraju
9 | Basement-2 | Mechanical Ventilation-Axial Fans | Electro Mechanical | Witt India Pvt.Ltd., | 2016-07-30 | Yes | Yes | Yes | Yes | Yes | July-2016 to Jan-2018 | 7TH FLOOR, BLOCK A, Q-CITY, GACHIBOWLI, NANAKRAMGUDA, HYD-500046 | No | Manoharu | N.Rama Krishnamraju
10 |  | Mechanical Ventilation-Jet Fan | Electro Mechanical | Witt India Pvt.Ltd., | 2016-07-30 | Yes | Yes | Yes | Yes | Yes |  |  | No | Manoharu | N.Rama Krishnamraju
11 | Basement-2 | STP Ventilation System | EM | Witt India Pvt.Ltd., | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | 7TH FLOOR, BLOCK A, Q-CITY, GACHIBOWLI, NANAKRAMGUDA, HYD-500046 | No | Manoharu | N.Rama Krishnamraju
12 | All Blocks + Club House Lifts | Elevators | Electro Mechanical | Mitsubishi | We provide Individual lifts Commissioning in Excel sheet | Yes | Yes | Yes | Yes | Yes | We provide Individual lifts AMC in Excel sheet | HYD PH.NO:(040-27546738), FAX NO: (914027546739) | No | Manoharu | N.Rama Krishnamraju
13 | Club House Service Lift | Service Elevators | Electro Mechanical | Johnson | 2016-04-08 | Yes | Yes | Yes | Yes | Yes | 08-04-2016 to 07-10-2016 | Plot No. B-31, TIE balanagar, Hyd-500037 Phn:23073881/82/83 , Mail Id: hyderabad@johnsonliftsltd.com | No | Narasimhulu | N.Rama Krishnamraju
14 | C,F,H Blocks T/F Yard podium | DG Set's | Electro Mechanical | Bhagya Nagar Diesel's | We provide Individual DG sets Commissioning in Excel sheet | Yes | Yes | Yes | Yes | NO | We provide Individual DG warranty in Excel sheet | M/S.Bhagya nagar Diesels H.No:5-9-286/2/65, Flat No.65, Near andhara Jyothi Press, rajiv Gandhi Nagar, Moosapet, Kukatpally, Hyd-500072 | No | Manoharu | N.Rama Krishnamraju
15 | C,F,H Blocks T/F Yard podium | Transformers | Electrical | PETE- Hammond Power Sloutions Pvt. Ltd., | 2016-05-03 | Yes | Yes | Yes | Yes | Yes | Sep-15 to aug-17 | Corporate office: G-9 to 11, Bhavya's sree Arcade, D.No:8-3-166/6&7, erragadda,Hyd-500018, Ph:+91-040-23813593/23812291, Marketing: +91-9700041717/ marketing@petetransformers.com, Servicing:+91-9700041818/ servicing@petetransformers.com WORKS: Plot No6A, Phase-1, Pashammailaram, patancheru,Medak dist -502307 Ph:+91-8455-224124 Email:works@petetransformers.com, www.petetransformers.com | No | Manoharu | N.Rama Krishnamraju
16 | C,F,H Blocks T/F Yard podium | Tap Changer | Electro Mechanical | ON Load Gears | 2016-05-03 | Yes | Yes | Yes | Yes | NO | Sep-15 to aug-17 | ON Load Gears 432,433, SIDCO Estate,88, Yadhaval Street, Ambattur, Chennai-600098, Ph:43935811, 43935813, 43935800, Fax:044-43935888,26257690, Email:olg@md2.vsnl.net.in, web:www.onloadgears.com | No | Manoharu | N.Rama Krishnamraju
17 | Club house Terrace | Swimming Pool Pump Room | Electro Mechanical | Clear Water Pool's | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | FLAT NO.F4,SEVERA RESIDENCY,HOUSE NO.8-3-167/9, ERRAGADDA, HYD-500018 | No | Sarvanan | N.Rama Krishnamraju
18 | Central Lawn | Central Fountain | Electro Mechanical | Clear Water Pool's | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | FLAT NO.F4,SEVERA RESIDENCY,HOUSE NO.8-3-167/9, ERRAGADDA, HYD-500018 | No | Sarvanan | N.Rama Krishnamraju
19 | Main Gate Entrance | Main Gate water Body | Electro Mechanical | Clear Water Pool's | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | FLAT NO.F4,SEVERA RESIDENCY,HOUSE NO.8-3-167/9, ERRAGADDA, HYD-500018 | No | Sarvanan | N.Rama Krishnamraju
20 | Main Gate Entry & exit | Automatic Hydraulic Boom Barrier | Electronic | V & S Technologies | 2016-09-06 | Yes | Yes | Yes | Yes | Yes | 06-09-2016 to 06-09-2018 | V & S Technologies, #301,Kaizen imerial Heights, Street No-2, Uma Nagar, Kundan bagh, Begumpet, Hyd-500016, Contacts: landline:040-66610622/23404535, Mobile:+918498099901/02, Email:info@alliancesecuritysystems.com, alliance_powerfence@hotmail.com | No | R.Srinivas | N.Rama Krishnamraju
21 | Boundry Wall | Solar Fencing | Electrical | V & S Technologies | 2016-07-01 | Yes | Yes | Yes | Yes | Yes | July-2016 to 01-08-2017 |  | No | Manoharu | N.Rama Krishnamraju
22 | All Blocks terrace | Solar water Heaters | Electrical | VK Engineers | 2016-08-06 | Yes | Yes | Yes | Yes | NO | 06-08-2016 to 05-08-2018 | VK Engineers Flat no:-105, Tulasi Residency, Back side of narayana Jr college, Chintal, Qutbullapur mandal, R.R.Dist., Hyd-54. Ph:040-23172317, mobile:8096002251/52/54 Web:www.vkengineershyd.in Email:hr@vkengineershyd.in | No | Manoharu | N.Rama Krishnamraju
23 | All Blocks+ Club House + Main Gate + STP | CCTV | Electronic | Protocol India Pvt.Ltd., | 2016-07-28 | Yes | Yes | Yes | Yes | Yes | 28-07-2016 to 27-07-2018 | Plot No.235,4th Floor, Sai Sadam,SOI Employee Society, Madhapur,Hyderabad-500081 | No | Chaitanya | N.Rama Krishnamraju
24 | Storm Water Pumps | Strom Water Pumps | EM | Revolve Engineers | 2016-02-15 | Yes | Yes | Yes | Yes | NO | 2017-02-14 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Mahesh | N.Rama Krishnamraju
25 | Oozing Pits | Oozing Pumps | EM | Revolve Engineers | 2016-01-20 | Yes | Yes | Yes | Yes | NO | 2017-01-19 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Mahesh | N.Rama Krishnamraju
26 | All Blocks Terrace | Solar power panels | Electrical | Energy Exchange India Limited | We provide Individual blocks Commissioning in Excel sheet | Yes | Yes | yes | yes | NO | We provide Individual blocks warranty in Excel sheet | Name:Krishna Kumar K, Phn:+919849085747, Mail:@kk@enxindia.com, Name:Pedhi Raju Bh, Phn:+919848037227 Mail:raju@enxindia.com, PlotNo.235,45th Floor, Sai sadan, SOI Employee society, Madhapur, Hyd-500081, Ph:+919666666679. | No | Krishna Kumar | N.Rama Krishnamraju
27 | External Electrical Works | External Electrical Works | Electrical | Tejha Power Controls Pvt.Ltd | 2016-05-05 | Yes | Yes | yes | yes | yes | 05-05-2016 to 04-05-2017 | Off & Fac:23045266, Fax:23041804, Email:tejhapc@yahoo.co.in, Off:Flat No.401, NVS Residency, Huda Colony, chandanagar, Hyd-500050 | No | Manoharu | N.Rama Krishnamraju
28 | All Blocks | Energy Meters | Electrical | Elmesaure India Pvt Ltd | 2016-05-01 | Yes | Yes | yes | yes | NO | Mar-2015 to Mar-2017 (320) and Sep-2015 to Sep-2017(400) | Elmeasure India Private Limited #764, 4th Phase, 707, Yelahanka New Town, Bangalore-560064 Karnataka, Ph:+918028461777,32904489,28461744, Telefax:+918041272461, Email:contactblr@elmeasure.com, www.elmeasure.com | No | Bharath | N.Rama Krishnamraju
29 | All Blocks | Gas Meters | Gas | Eminent gas | 2016-07-01 | Yes | Yes | yes | yes | Yes | Jul-16 to june-17 | M.S.Kishore(Managing Director) Ph:9323744210, M.C.Sekhar(Director) Ph:9866404076 M/S Eminent Gas Technologies Pvt Ltd., Shop no-B21&B22, Lakshmi Complex, Erragadda, Hyd-500018. | No | Chandra shekar | N.Rama Krishnamraju
30 | Podium | Irrigation | Horticulture | Kaveri irrigations | 2016-08-26 | Yes | Yes | Yes | Yes | Yes | 26-08-2016 to 25-08-2017 | Kaveri irrigations Gomukhi point, 102, Sangu nagar, EB complex back side, Collectorate post, Erode-district, Pin-638011,Tamilnadu,india. Tel/fax:+91-424-2273032,2273033, Mobile:+91-94433-60700 Email:ssivam5@yahoo.com | No | Rajamouli | N.Rama Krishnamraju
31 | All blocks | Intercom | Protocol | Nextel Protocol online pvt.ltd., | 2016-04-05 | Yes | Yes | Yes | No | NO |  | Nextel Protocol online pvt.ltd., Flat no.301,Spline Arcde, plot 1208, Ayyapa society, Madhapur, hyd-500081. Mr. K.Krishna Kumar Mobile:9849085747 Email:kk@protocolnet.com
32 | A-Block | Video Door Bell | Protocol | AA Enterprises | 2016-08-11 | Yes | Yes | yes | yes | yes | 11-08-2016 to 10-08-2017 | AA enterprises #5-2-428/429, 3rd floor, Hyderbasti, R.P.Road, secunderabad-500003,Telangana State. Tele:9701744400,9849548400 Email:aaenterprisess@gmail.com,gmk@aaenterprises.co.in, Web: www.aaenterprises.co.in | no | Manoharu | N.Rama Krishnamraju
33 | Podium | External Electrical lightning Works | Electrical | Tejha Power Controls Pvt.Ltd | 2016-07-01 | Yes | Yes | yes | yes | yes | 2017-06-30 | Off & Fac:23045266, Fax:23041804, Email:tejhapc@yahoo.co.in, Off:Flat No.401, NVS Residency, Huda Colony, chandanagar, Hyd-500050 | No | Manoharu | N.Rama Krishnamraju
34 | A to F-blocks | Internal Electrical works | Electrical | Sai balaji infra(india) pvt ltd. | 2016-03-01 | Yes | Yes | yes | yes | yes | 2017-02-28 | Plot No:405 block II, Srikalayani RBR complex, Miyapur, Hyderabad,Ph:9848246533-Ramprabhu | No | Manoharu | N.Rama Krishnamraju
35 | G to I-Blocks | Internal Electrical works | Electrical | Sai Ganesh Electricals | 2016-06-01 | Yes | Yes | yes | yes | yes | 01-06-2016 to 31-05-2017 | Sai Ganesh Electricals, Plot No.13-9-1/3/31/1/c, Radha krishna nagar, Borabanda , Hyd, Ph:9948561236-Vasu babu |  | Manoharu | N.Rama Krishnamraju
36 | A&H-blocks | Internal Plumbing | Plumbing | Sri sairam constructions | 2016-05-29 | Yes | Yes | yes | yes | yes | 2017-05-28 | M.venkat reddy,S.suresh reddy H.No-1-85 third floor near netagi bhavan,Nallagandla, serilingampally 500019 Ph:9845406244,9866640835 | No | Suresh Reddy | N.Rama Krishnamraju
37 | B,C,G&F-Blocks | Internal Plumbing | Plumbing | Sri sai plumbing works | 2016-05-30 | Yes | Yes | yes | yes | yes | 2017-05-29 | N.Swamy,N.Samapth kumar H.No:1-110/A/48, Gopal reddy nagar, Kondapur-500084,Ph:9949300523,9394559995 | No | Swamy | N.Rama Krishnamraju
38 | D,E,I&Club house-Blocks | Internal Plumbing | Plumbing | Agpa Engineering& Company | 2016-08-01 | Yes | Yes | yes | yes | yes | 2017-07-31 | H-No:1/18,Nankaramguda,RR,Hyd-500018, Ph:9908945107,9963885749 | No | Swamy | N.Rama Krishnamraju
39 | A to I blocks | External Sewage&Rain Water system | Plumbing | Sri sairam constructions | 2016-05-30 | Yes | Yes | yes | yes | yes | 2017-05-29 | M.venkat reddy,S.suresh reddy H.No-1-85 third floor near netagi bhavan,Nallagandla, serilingampally 500019 Ph:9845406244,9866640835 | No | Suresh Reddy | N.Rama Krishnamraju
40 | A to I blocks | External Storm Water drainage system | Plumbing | Sri sai plumbing works | 2016-05-30 | Yes | Yes | yes | yes | yes | 2017-05-29 | N.Swamy,N.Samapth kumar H.No:1-110/A/48, Gopal reddy nagar, Kondapur-500084,Ph:9949300523,9394559995 | No | Swamy | N.Rama Krishnamraju
41 | A to I blocks | External surface drainage & Podium drain system | Plumbing | Agpa Engineering& Company | 2016-08-01 | Yes | Yes | yes | yes | yes | 2017-07-31 | H-No:1/18,Nankaramguda,RR,Hyd-500018, Ph:9908945107,9963885749 | No | Swamy | N.Rama Krishnamraju
| Checked By |  |  | Handing Over By |  |  |  |  | Handed Over By |  |  | Tanken Over By
| Project Head |  |  | PMC |  |  |  |  | Project-PM |  |  | APMS Incharge

## Sheet1
Aparna Sarovar Grande
List Of Equipment/Assets - Handing Over - Taking Over Documents Report
S.No | Location | Type Equipment | Catogery | Vendor | Commissioning Details | WO | PO | BOQ | Manual | Drawings | Warranty Details | Vendor Contacts | Pending DOC'S | Project Handover Coordinator | Taken Over By | Status | Remarks
1 | A-block Basement-2 | STP | Electrical& Electro Mechanical | Revolve Engineers | 2016-05-01 | Yes | Yes | Yes | Yes | Yes | May-16 to April-18 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Revolve-Vijay | N.Rama Krishnamraju |  | Centrifuge Commissioning not completed
2 | A-block Basement-2 | Hydro-Pneumatic system for STP | Electrical& Electro Mechanical | Revolve Engineers | 2016-06-01 | Yes | Yes | Yes | Yes | NO | june-2016 to june-2017 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Revolve-Suresh | N.Rama Krishnamraju
3 | A-block Basement-2 | Hydro-Pneumatic system for Metro water supply | Electrical& Electro Mechanical | Revolve Engineers | 2015-09-15 | Yes | Yes | Yes | Yes | NO | sep-15 to aug-16 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Revolve-Suresh | N.Rama Krishnamraju
4 | A-block Basement-2 | Hydro-Pneumatic system for Domestic water supply | Electrical& Electro Mechanical | Revolve Engineers | 2015-09-15 | Yes | Yes | Yes | Yes | NO | sep-15 to aug-16 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Revolve-Suresh | N.Rama Krishnamraju
5 | A-block Basement-2 | Softening Plant | Mechanical | Coron India | 2015-11-28 | Yes | Yes | Yes | Yes | Yes | 28-11-2015 to 27-11-2016 | NO.231,SRIRAM, 1ST FLOOR, 5TH AIN, JRD TATA NAGAR, KODIGEHALLI, BANGALORE-560092 | No | Kamal | N.Rama Krishnamraju
|  | Pump's | Electrical& Electro Mechanical | Revolve Engineers | 2015-11-28 | Yes | Yes | Yes | Yes | NO | 28-11-2015 to 27-11-2016 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Revolve-Suresh | N.Rama Krishnamraju
6 | Basement-2 | Fire & Safety (A to D) | Mechanical | Sujay | 2015-11-20 | Yes | Yes | Yes | Yes | Yes | 20-11-15 to19-11-16 | 5-9-286/2/75, Plot No.75, Rajeevgandi Nagar, Prasanthi Nagar extn, I.E Kukatpally, Hyd-500072 | No | Naresh | Naveen prasad & N.Rama Krishnamraju
7 | Basement-2 | Fire & Safety (E to I) | Mechanical | Decars | 2016-08-08 | Yes | Yes | Yes | Yes | Yes | 08-08-2016 to 07-08-2017 | 1-10-212/2, St No:6, ASHOK NAGAR, HYD-500020 | No | M.Praveen Kumar | Naveen prasad & N.Rama Krishnamraju
8 | Basement-2 | Fire Jockey, Main&DG Pumps | Electro Mechanical | Revolve Engineers | 2015-11-20 | Yes | Yes | Yes | Yes | Yes | 20-11-15 to19-11-16 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Mahesh | Naveen prasad & N.Rama Krishnamraju
9 | Basement-2 | Mechanical Ventilation-Axial Fans | Electro Mechanical | Witt India Pvt.Ltd., | 2016-07-30 | Yes | Yes | Yes | Yes | Yes | July-2016 to Jan-2018 | 7TH FLOOR, BLOCK A, Q-CITY, GACHIBOWLI, NANAKRAMGUDA, HYD-500046 | No | Manoharu | N.Rama Krishnamraju
10 |  | Mechanical Ventilation-Jet Fan | Electro Mechanical | Witt India Pvt.Ltd., | 2016-07-30 | Yes | Yes | Yes | Yes | Yes |  |  | No | Manoharu | N.Rama Krishnamraju
11 | Basement-2 | STP Ventilation System | EM | Witt India Pvt.Ltd., | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | 7TH FLOOR, BLOCK A, Q-CITY, GACHIBOWLI, NANAKRAMGUDA, HYD-500046 | No | Manoharu | N.Rama Krishnamraju
12 | All Blocks + Club House Lifts | Elevators | Electro Mechanical | Mitsubishi | We provide Individual lifts Commissioning in Excel sheet | Yes | Yes | Yes | Yes | Yes | We provide Individual lifts AMC in Excel sheet | HYD PH.NO:(040-27546738), FAX NO: (914027546739) | No | Manoharu | N.Rama Krishnamraju
13 | Club House Service Lift | Service Elevators | Electro Mechanical | Johnson | 2016-04-08 | Yes | Yes | Yes | Yes | Yes | 08-04-2016 to 07-10-2016 | Plot No. B-31, TIE balanagar, Hyd-500037 Phn:23073881/82/83 , Mail Id: hyderabad@johnsonliftsltd.com | No | Narasimhulu | N.Rama Krishnamraju
14 | C,F,H Blocks T/F Yard podium | DG Set's | Electro Mechanical | Bhagya Nagar Diesel's | We provide Individual DG sets Commissioning in Excel sheet | Yes | Yes | Yes | Yes | NO | We provide Individual DG warranty in Excel sheet | M/S.Bhagya nagar Diesels H.No:5-9-286/2/65, Flat No.65, Near andhara Jyothi Press, rajiv Gandhi Nagar, Moosapet, Kukatpally, Hyd-500072 | No | Manoharu | N.Rama Krishnamraju
15 | C,F,H Blocks T/F Yard podium | Transformers | Electrical | PETE- Hammond Power Sloutions Pvt. Ltd., | 2016-05-03 | Yes | Yes | Yes | Yes | Yes | Sep-15 to aug-17 | Corporate office: G-9 to 11, Bhavya's sree Arcade, D.No:8-3-166/6&7, erragadda,Hyd-500018, Ph:+91-040-23813593/23812291, Marketing: +91-9700041717/ marketing@petetransformers.com, Servicing:+91-9700041818/ servicing@petetransformers.com WORKS: Plot No6A, Phase-1, Pashammailaram, patancheru,Medak dist -502307 Ph:+91-8455-224124 Email:works@petetransformers.com, www.petetransformers.com | No | Manoharu | N.Rama Krishnamraju
16 | C,F,H Blocks T/F Yard podium | Tap Changer | Electro Mechanical | ON Load Gears | 2016-05-03 | Yes | Yes | Yes | Yes | NO | Sep-15 to aug-17 | ON Load Gears 432,433, SIDCO Estate,88, Yadhaval Street, Ambattur, Chennai-600098, Ph:43935811, 43935813, 43935800, Fax:044-43935888,26257690, Email:olg@md2.vsnl.net.in, web:www.onloadgears.com | No | Manoharu | N.Rama Krishnamraju
17 | Club house Terrace | Swimming Pool Pump Room | Electro Mechanical | Clear Water Pool's | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | FLAT NO.F4,SEVERA RESIDENCY,HOUSE NO.8-3-167/9, ERRAGADDA, HYD-500018 | No | Sarvanan | N.Rama Krishnamraju
18 | Central Lawn | Central Fountain | Electro Mechanical | Clear Water Pool's | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | FLAT NO.F4,SEVERA RESIDENCY,HOUSE NO.8-3-167/9, ERRAGADDA, HYD-500018 | No | Sarvanan | N.Rama Krishnamraju
19 | Main Gate Entrance | Main Gate water Body | Electro Mechanical | Clear Water Pool's | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | FLAT NO.F4,SEVERA RESIDENCY,HOUSE NO.8-3-167/9, ERRAGADDA, HYD-500018 | No | Sarvanan | N.Rama Krishnamraju
20 | Main Gate Entry & exit | Automatic Hydraulic Boom Barrier | Electronic | V & S Technologies | 2016-09-06 | Yes | Yes | Yes | Yes | Yes | 06-09-2016 to 06-09-2018 | V & S Technologies, #301,Kaizen imerial Heights, Street No-2, Uma Nagar, Kundan bagh, Begumpet, Hyd-500016, Contacts: landline:040-66610622/23404535, Mobile:+918498099901/02, Email:info@alliancesecuritysystems.com, alliance_powerfence@hotmail.com | No | R.Srinivas | N.Rama Krishnamraju
21 | Boundry Wall | Solar Fencing | Electrical | V & S Technologies | 2016-07-01 | Yes | Yes | Yes | Yes | Yes | July-2016 to 01-08-2017 |  | No | Manoharu | N.Rama Krishnamraju
22 | All Blocks terrace | Solar water Heaters | Electrical | VK Engineers | 2016-08-06 | Yes | Yes | Yes | Yes | NO | 06-08-2016 to 05-08-2018 | VK Engineers Flat no:-105, Tulasi Residency, Back side of narayana Jr college, Chintal, Qutbullapur mandal, R.R.Dist., Hyd-54. Ph:040-23172317, mobile:8096002251/52/54 Web:www.vkengineershyd.in Email:hr@vkengineershyd.in | No | Manoharu | N.Rama Krishnamraju
23 | All Blocks+ Club House + Main Gate + STP | CCTV | Electronic | Protocol India Pvt.Ltd., | 2016-07-28 | Yes | Yes | Yes | Yes | Yes | 28-07-2016 to 27-07-2018 | Plot No.235,4th Floor, Sai Sadam,SOI Employee Society, Madhapur,Hyderabad-500081 | No | Chaitanya | N.Rama Krishnamraju
24 | Storm Water Pumps | Strom Water Pumps | EM | Revolve Engineers | 2016-02-15 | Yes | Yes | Yes | Yes | NO | 2017-02-14 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Mahesh | N.Rama Krishnamraju
25 | Oozing Pits | Oozing Pumps | EM | Revolve Engineers | 2016-01-20 | Yes | Yes | Yes | Yes | NO | 2017-01-19 | Revolve Engineers PLOT NO.52,H.NO.7-1-282/C/52/C, LINGAIAH NAGAR, BALKAMPET,HYDERABAD-500018. Contact person:Mr.Suresh Babu Mobile:9701205566, Ph:+91-040-44545100 to129, +91-40-23810205, Telefax:+91-040-44545103, Service center:+91-40-65545624, Email:info@revolveengineers.com | No | Mahesh | N.Rama Krishnamraju
26 | All Blocks Terrace | Solar power panels | Electrical | Energy Exchange India Limited | We provide Individual blocks Commissioning in Excel sheet | Yes | Yes | yes | yes | NO | We provide Individual blocks warranty in Excel sheet | Name:Krishna Kumar K, Phn:+919849085747, Mail:@kk@enxindia.com, Name:Pedhi Raju Bh, Phn:+919848037227 Mail:raju@enxindia.com, PlotNo.235,45th Floor, Sai sadan, SOI Employee society, Madhapur, Hyd-500081, Ph:+919666666679. | No | Krishna Kumar | N.Rama Krishnamraju
27 | External Electrical Works | External Electrical Works | Electrical | Tejha Power Controls Pvt.Ltd | 2016-05-05 | Yes | Yes | yes | yes | yes | 05-05-2016 to 04-05-2017 | Off & Fac:23045266, Fax:23041804, Email:tejhapc@yahoo.co.in, Off:Flat No.401, NVS Residency, Huda Colony, chandanagar, Hyd-500050 | No | Manoharu | N.Rama Krishnamraju
28 | All Blocks | Energy Meters | Electrical | Elmesaure India Pvt Ltd | 2016-05-01 | Yes | Yes | yes | yes | NO | Mar-2015 to Mar-2017 (320) and Sep-2015 to Sep-2017(400) | Elmeasure India Private Limited #764, 4th Phase, 707, Yelahanka New Town, Bangalore-560064 Karnataka, Ph:+918028461777,32904489,28461744, Telefax:+918041272461, Email:contactblr@elmeasure.com, www.elmeasure.com | No | Bharath | N.Rama Krishnamraju
29 | All Blocks | Gas Meters | Gas | Eminent gas | 2016-07-01 | Yes | Yes | yes | yes | Yes | Jul-16 to june-17 | M.S.Kishore(Managing Director) Ph:9323744210, M.C.Sekhar(Director) Ph:9866404076 M/S Eminent Gas Technologies Pvt Ltd., Shop no-B21&B22, Lakshmi Complex, Erragadda, Hyd-500018. | No | Chandra shekar | N.Rama Krishnamraju
30 | Podium | Irrigation | Horticulture | Kaveri irrigations | 2016-08-26 | Yes | Yes | Yes | Yes | Yes | 26-08-2016 to 25-08-2017 | Kaveri irrigations Gomukhi point, 102, Sangu nagar, EB complex back side, Collectorate post, Erode-district, Pin-638011,Tamilnadu,india. Tel/fax:+91-424-2273032,2273033, Mobile:+91-94433-60700 Email:ssivam5@yahoo.com | No | Rajamouli | N.Rama Krishnamraju
31 | All blocks | Intercom | Protocol | Nextel Protocol online pvt.ltd., | 2016-04-05 | Yes | Yes | Yes | No | NO |  | Nextel Protocol online pvt.ltd., Flat no.301,Spline Arcde, plot 1208, Ayyapa society, Madhapur, hyd-500081. Mr. K.Krishna Kumar Mobile:9849085747 Email:kk@protocolnet.com
32 | A-Block | Video Door Bell | Protocol | AA Enterprises | 2016-08-11 | Yes | Yes | yes | yes | yes | 11-08-2016 to 10-08-2017 | AA enterprises #5-2-428/429, 3rd floor, Hyderbasti, R.P.Road, secunderabad-500003,Telangana State. Tele:9701744400,9849548400 Email:aaenterprisess@gmail.com,gmk@aaenterprises.co.in, Web: www.aaenterprises.co.in | no | Manoharu | N.Rama Krishnamraju
33 | Podium | External Electrical lightning Works | Electrical | Tejha Power Controls Pvt.Ltd | 2016-07-01 | Yes | Yes | yes | yes | yes | 2017-06-30 | Off & Fac:23045266, Fax:23041804, Email:tejhapc@yahoo.co.in, Off:Flat No.401, NVS Residency, Huda Colony, chandanagar, Hyd-500050 | No | Manoharu | N.Rama Krishnamraju
34 | A to F-blocks | Internal Electrical works | Electrical | Sai balaji infra(india) pvt ltd. | 2016-03-01 | Yes | Yes | yes | yes | yes | 2017-02-28 | Plot No:405 block II, Srikalayani RBR complex, Miyapur, Hyderabad,Ph:9848246533-Ramprabhu | No | Manoharu | N.Rama Krishnamraju
35 | G to I-Blocks | Internal Electrical works | Electrical | Sai Ganesh Electricals | 2016-06-01 | Yes | Yes | yes | yes | yes | 01-06-2016 to 31-05-2017 | Sai Ganesh Electricals, Plot No.13-9-1/3/31/1/c, Radha krishna nagar, Borabanda , Hyd, Ph:9948561236-Vasu babu |  | Manoharu | N.Rama Krishnamraju
36 | A&H-blocks | Internal Plumbing | Plumbing | Sri sairam constructions | 2016-05-29 | Yes | Yes | yes | yes | yes | 2017-05-28 | M.venkat reddy,S.suresh reddy H.No-1-85 third floor near netagi bhavan,Nallagandla, serilingampally 500019 Ph:9845406244,9866640835 | No | Suresh Reddy | N.Rama Krishnamraju
37 | B,C,G&F-Blocks | Internal Plumbing | Plumbing | Sri sai plumbing works | 2016-05-30 | Yes | Yes | yes | yes | yes | 2017-05-29 | N.Swamy,N.Samapth kumar H.No:1-110/A/48, Gopal reddy nagar, Kondapur-500084,Ph:9949300523,9394559995 | No | Swamy | N.Rama Krishnamraju
38 | D,E,I&Club house-Blocks | Internal Plumbing | Plumbing | Agpa Engineering& Company | 2016-08-01 | Yes | Yes | yes | yes | yes | 2017-07-31 | H-No:1/18,Nankaramguda,RR,Hyd-500018, Ph:9908945107,9963885749 | No | Swamy | N.Rama Krishnamraju
39 | A to I blocks | External Sewage&Rain Water system | Plumbing | Sri sairam constructions | 2016-05-30 | Yes | Yes | yes | yes | yes | 2017-05-29 | M.venkat reddy,S.suresh reddy H.No-1-85 third floor near netagi bhavan,Nallagandla, serilingampally 500019 Ph:9845406244,9866640835 | No | Suresh Reddy | N.Rama Krishnamraju
40 | A to I blocks | External Storm Water drainage system | Plumbing | Sri sai plumbing works | 2016-05-30 | Yes | Yes | yes | yes | yes | 2017-05-29 | N.Swamy,N.Samapth kumar H.No:1-110/A/48, Gopal reddy nagar, Kondapur-500084,Ph:9949300523,9394559995 | No | Swamy | N.Rama Krishnamraju
41 | A to I blocks | External surface drainage & Podium drain system | Plumbing | Agpa Engineering& Company | 2016-08-01 | Yes | Yes | yes | yes | yes | 2017-07-31 | H-No:1/18,Nankaramguda,RR,Hyd-500018, Ph:9908945107,9963885749 | No | Swamy | N.Rama Krishnamraju
| Checked By |  |  | Handing Over By |  |  |  |  | Handed Over By |  |  | Tanken Over By
| Project Head |  |  | PMC |  |  |  |  | Project-PM |  |  | APMS Incharge

## DG warranty
S.No | Location | Type Equipment | Catogery | Vendor | Commissioning Details | BOQ | Manual | Drawings | Warranty Details | Vendor Contacts | Pending DOC'S | Project Handover Coordinator | Taken Over By | Remarks
| C-Block podium | Electro Mechanical | DG | Bhagya Nagar Diesel's | 2016-05-23 | Yes | Yes | Yes | 2018-03-23 | M/s.Bhagya nagar Diesels Mr.Sathibabu(service manager)-8008484858, Mr.Kalyan (Head Manager)- 8790900550, customer care:040-23071199/9177111299 | No | Manoharu | N.Rama Krishnamraju
| C-Block podium | Electro Mechanical | DG | Bhagya Nagar Diesel's | 2016-01-08 | Yes | Yes | Yes | 2017-11-08 |  | No | Manoharu | N.Rama Krishnamraju
| F-Block podium | Electro Mechanical | DG | Bhagya Nagar Diesel's | 2016-05-23 | Yes | Yes | Yes | 2018-03-23 |  | No | Manoharu | N.Rama Krishnamraju
| F-Block podium | Electro Mechanical | DG | Bhagya Nagar Diesel's | 2016-05-23 | Yes | Yes | Yes | 2018-03-23 |  | No | Manoharu | N.Rama Krishnamraju
| H-Block podium | Electro Mechanical | DG | Bhagya Nagar Diesel's | 2015-12-03 | Yes | Yes | Yes | 2017-10-03 |  | No | Manoharu | N.Rama Krishnamraju
| H-Block podium | Electro Mechanical | DG | Bhagya Nagar Diesel's | 2016-05-06 | Yes | Yes | Yes | 2018-03-06 |  | No | Manoharu | N.Rama Krishnamraju

## Solar panels Warranty
Location | Type Equipment | Catogery | Vendor | Commissioning Details | BOQ | Manual | Drawings | Warranty Details | Vendor Contacts | Pending DOC'S | Project Handover Coordinator | Taken Over By | Remarks
B-Block Terrace | Solar power panels | Electrical | Energy Exchange India Limited | 2015-05-10 | yes | yes | yes | 2020-05-09 | Name:Krishna Kumar K, Phn:+919849085747, Mail:@kk@enxindia.com, Name:Pedhi Raju Bh, Phn:+919848037227 Mail:raju@enxindia.com, PlotNo.235,45th Floor, Sai sadan, SOI Employee society, Madhapur, Hyd-500081, Ph:+919666666679. | No | Krishna Kumar | N.Rama Krishnamraju
C-Block Terrace | Solar power panels | Electrical | Energy Exchange India Limited | 2015-05-10 | yes | yes | yes | 2020-05-09 |  | No | Krishna Kumar | N.Rama Krishnamraju
D-Block Terrace | Solar power panels | Electrical | Energy Exchange India Limited | 2015-05-10 | yes | yes | yes | 2020-05-09 |  | No | Krishna Kumar | N.Rama Krishnamraju
E-Block Terrace | Solar power panels | Electrical | Energy Exchange India Limited | 2016-07-26 | yes | yes | yes | 2021-07-25 |  | No | Krishna Kumar | N.Rama Krishnamraju
F-Block Terrace | Solar power panels | Electrical | Energy Exchange India Limited | 2016-07-26 | yes | yes | yes | 2021-07-25 |  | No | Krishna Kumar | N.Rama Krishnamraju
G-Block Terrace | Solar power panels | Electrical | Energy Exchange India Limited | 2016-04-27 | yes | yes | yes | 2021-04-26 | Make : Akshaya Solar Power (INDIA) PVT.LTD. Regd.Off.&Factory:PlotNo. 60/C/E, Phase-1,IDA,Jeedimetla,HYD-500055.T.S.India Tel:+91-40-40064523, Fax:+91-40-40064524 Email:raju@akshayasolar.com, www.akshayasolar.com | No | Raju | N.Rama Krishnamraju
H-Block Terrace | Solar power panels | Electrical | Energy Exchange India Limited | 2016-07-26 | yes | yes | yes | 2021-07-25 |  | No | Raju | N.Rama Krishnamraju
I-Block Terrace | Solar power panels | Electrical | Energy Exchange India Limited | 2016-04-27 | yes | yes | yes | 2021-04-26 |  | No | Raju | N.Rama Krishnamraju

## Sheet2
Aparna Sarovar Grande
Facilities/MEP services Hoto-Report Date:
S.No | Location | Type Equipment | Catogery | Vendor | Date of commissioning | WO | PO | BOQ | Manual | Drawings | Period of Warranty | Pending DOC'S | Handover By | Taken Over By | Status | File no. | Remarks
1 | A-block Basement-2 | STP | Electrical& Electro Mechanical | Revolve Engineers | 2016-05-01 | Yes | Yes | Yes | Yes | Yes | May-16 to April-18 | No
2 | A-block Basement-2 | Hydro-Pneumatic system for STP | Electrical& Electro Mechanical | Revolve Engineers | 2016-06-01 | Yes | Yes | Yes | Yes | NO | june-2016 to june-17 | No
3 | A-block Basement-2 | Hydro-Pneumatic system for Metro water supply | Electrical& Electro Mechanical | Revolve Engineers | 2015-09-15 | Yes | Yes | Yes | Yes | NO | sep-15 to aug-16 | No
4 | A-block Basement-2 | Hydro-Pneumatic system for Domestic water supply | Electrical& Electro Mechanical | Revolve Engineers | 2015-09-15 | Yes | Yes | Yes | Yes | NO | sep-15 to aug-16 | No
5 | A-block Basement-2 | Softening Plant | Mechanical | Coron India | 2015-11-28 | Yes | Yes | Yes | Yes | Yes | 28-11-2015 to 27-11-2016 | No
5 | A-block Basement-2 | Pump's | Electrical& Electro Mechanical | Revolve Engineers | 2015-11-28 | Yes | Yes | Yes | Yes | NO | 28-11-2015 to 27-11-2016 | No
6 | Basement-2 | Fire & Safety (A to D) | Mechanical | Sujay | 2015-11-20 | Yes | Yes | Yes | Yes | Yes | 20-11-15 to 19-11-16 | No
7 | Basement-2 | Fire & Safety (E to I) | Mechanical | Decars | 2016-08-08 | Yes | Yes | Yes | Yes | Yes | 08-08-2016 to 07-08-2017 | No
8 | Basement-2 | Fire Jockey, Main&DG Pumps | Electro Mechanical | Revolve Engineers | 2015-11-20 | Yes | Yes | Yes | Yes | Yes | 20-11-15 to 19-11-16 | No
9 | Basement-2 | Mechanical Ventilation-Axial Fans | Electro Mechanical | Witt India Pvt.Ltd., | 2016-07-30 | Yes | Yes | Yes | Yes | Yes | July-2016 to Jan-2018 | No
10 | Basement-2 | Mechanical Ventilation-Jet Fan | Electro Mechanical | Witt India Pvt.Ltd., | 2016-07-30 | Yes | Yes | Yes | Yes | Yes |  | No
11 | Basement-2 | STP Ventilation System | EM | Witt India Pvt.Ltd., | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | No
12 | All Blocks + Club House Lifts | Elevators | Electro Mechanical | Mitsubishi |  | Yes | Yes | Yes | Yes | Yes |  | No
Page no.1
Aparna Sarovar Grande
Facilities/MEP services Hoto-Report Date:
13 | Club House Service Lift | Service Elevators | Electro Mechanical | Johnson | 2016-04-08 | Yes | Yes | Yes | Yes | Yes | 08-04-2016 to 07-10-2016 | No
14 | C,F,H Blocks T/F Yard podium | DG Set's | Electro Mechanical | Bhagya Nagar Diesel's |  | Yes | Yes | Yes | Yes | NO |  | No
15 | C,F,H Blocks T/F Yard podium | Transformers | Electrical | PETE- Hammond Power Sloutions Pvt. Ltd., | 2016-05-03 | Yes | Yes | Yes | Yes | Yes | Sep-15 to aug-17 | No
16 | C,F,H Blocks T/F Yard podium | Tap Changer | Electro Mechanical | ON Load Gears | 2016-05-03 | Yes | Yes | Yes | Yes | NO | Sep-15 to aug-17 | No
17 | Club house Terrace | Swimming Pool Pump Room | Electro Mechanical | Clear Water Pool's | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | No
18 | Central Lawn | Central Fountain | Electro Mechanical | Clear Water Pool's | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | No
19 | Main Gate Entrance | Main Gate water Body | Electro Mechanical | Clear Water Pool's | 2016-08-01 | Yes | Yes | Yes | Yes | Yes | Aug-2016 to July-2017 | No
20 | Main Gate Entry & exit | Automatic Hydraulic Boom Barrier | Electronic | V & S Technologies | 2016-09-06 | Yes | Yes | Yes | Yes | Yes | 06-09-2016 to 06-09-2018 | No
21 | Boundry Wall | Solar Fencing | Electrical | V & S Technologies | 2016-07-01 | Yes | Yes | Yes | Yes | Yes | July-2016 to 01-08-2017 | No
22 | All Blocks terrace | Solar water Heaters | Electrical | VK Engineers | 2016-08-06 | Yes | Yes | Yes | Yes | NO | 06-08-2016 to 05-08-2018 | No
23 | All Blocks+ Club House + Main Gate + STP | CCTV | Electronic | Protocol India Pvt.Ltd., | 2016-07-28 | Yes | Yes | Yes | Yes | Yes | 28-07-2016 to 27-07-2018 | No
24 | Storm Water Pumps | Strom Water Pumps | EM | Revolve Engineers | 2016-02-15 | Yes | Yes | Yes | Yes | NO | 2017-02-14 | No
25 | Oozing Pits | Oozing Pumps | EM | Revolve Engineers | 2016-01-20 | Yes | Yes | Yes | Yes | NO | 2017-01-19 | No
26 | All Blocks Terrace | Solar power panels | Electrical | Energy Exchange India Limited |  | Yes | Yes | yes | yes | NO |  | No
27 | External Electrical Works | External Electrical Works | Electrical | Tejha Power Controls Pvt.Ltd | 2016-05-05 | Yes | Yes | yes | yes | yes | 05-05-2016 to 04-05-17 | No
Page no.2
Aparna Sarovar Grande
Facilities/MEP services Hoto-Report Date:
28 | All Blocks | Energy Meters | Electrical | Elmesaure India Pvt Ltd | 2016-05-01 | Yes | Yes | yes | yes | NO | Mar-2015 to Mar-2017 (320) and Sep-2015 to Sep-2017 (400) | No
29 | All Blocks | Gas Meters | Gas | Eminent gas | 2016-07-01 | Yes | Yes | yes | yes | Yes | Jul-16 to june-17 | No
30 | Podium | Irrigation | Horticulture | Kaveri irrigations | 2016-08-26 | Yes | Yes | Yes | Yes | Yes | 26-08-2016 to 25-08-17 | No
31 | All blocks | Intercom | Protocol | Nextel Protocol online pvt.ltd., | 2016-04-05 | Yes | Yes | Yes | No | NO
32 | A-Block | Video Door Bell | Protocol | AA Enterprises | 2016-08-11 | Yes | Yes | yes | yes | yes | 11-08-2016 to 10-08-2017 | no
33 | Podium | External Electrical lightning Works | Electrical | Tejha Power Controls Pvt.Ltd | 2016-07-01 | Yes | Yes | yes | yes | yes | 2017-06-30 | No
34 | A to F-blocks | Internal Electrical works | Electrical | Sai balaji infra(india) pvt ltd. | 2016-03-01 | Yes | Yes | yes | yes | yes | 2017-02-28 | No
35 | G to I-Blocks | Internal Electrical works | Electrical | Sai Ganesh Electricals | 2016-06-01 | Yes | Yes | yes | yes | yes | 01-06-2016 to 31-05-17
36 | A&H-blocks | Internal Plumbing | Plumbing | Sri sairam constructions | 2016-05-29 | Yes | Yes | yes | yes | yes | 2017-05-28 | No
37 | B,C,G&F-Blocks | Internal Plumbing | Plumbing | Sri sai plumbing works | 2016-05-30 | Yes | Yes | yes | yes | yes | 2017-05-29 | No
38 | D,E,I&Club house-Blocks | Internal Plumbing | Plumbing | Agpa Engineering& Company | 2016-08-01 | Yes | Yes | yes | yes | yes | 2017-07-31 | No
39 | A to I blocks | External Sewage&Rain Water system | Plumbing | Sri sairam constructions | 2016-05-30 | Yes | Yes | yes | yes | yes | 2017-05-29 | No
40 | A to I blocks | External Storm Water drainage system | Plumbing | Sri sai plumbing works | 2016-05-30 | Yes | Yes | yes | yes | yes | 2017-05-29 | No
41 | A to I blocks | External surface drainage & Podium drain system | Plumbing | Agpa Engineering& Company | 2016-08-01 | Yes | Yes | yes | yes | yes | 2017-07-31 | No
Page no.3
|  | Handed Over By | [12 empty] | Taken Over By