## HOD Status of Elina.Blr
APARNA ELINA - LIST OF HANDING OVER DOCUMENTS
SL. NO | NAME OF THE PACKAGE | PO/ WO NO. | AREA OF WORK | NAME OF VENDOR | CONTACT DETAILS | FINAL BILL STATUS | HANDOVER STATUS | HANDOVER DOCUMENTS | [15 empty] | SIGN OFF |  | Remarks
[8 empty] | Concept Design Plan | Typical Unit plan | Specifications | Inventory Plumbing | Inventory Electrical | Civil Snags attended | PO/ Work Order copy | As-built drawings | Guarantee certificate | Guarantee certificate Date | Work completion certificate | Do's & don'ts | Checklists | Testing and commissioning certificates | Operation/ Maintenance Manuals | Warranty / Guarantee Period | Signature ACEPL | Signature APMS
1 | ARCHETECTURAL AS BUILD DRAWINGS |  | ELINA | M/s. RSP Design Consultants | M/s. Rsp Design Consultants Tel: 080-25596868 Fax: 080-25596818 Contact Person: Mr. Prasad Tel: 040-6697 7777 Email: info@genesisplanners.in
2 | STRUCTURAL AS BUILD DRAWINGS |  | ELINA | M/s. Design Tree Service consultants pvt ltd | M/s Design Tree service consultants pvt ltd Tel: 08041225481 Fax: 080-41225479 Contact Person: Mr. SAYEED Tel: 9848202822 Email: zakiassociates@gmail.com
3 | CLUB HOUSE INTERIOR DRAWINGS |  | CLUB HOUSE | M/s. MOHAN CONSULTANTS | MOHAN CONSULTANTS Architects, Interior designers #8-2-293/82/A/1016, Plot no:1016, Road no:46A, Jubilee hills,Hyderabad-500033, Telangana, India.Tel:+91-04-65865340, 23554450, 23554460. www.mohanconsultants.com
4 | Civil & Structural Works and Finishing works - FLAT WISE CHECKLISTS ( A & B ) BLOCKS | As per Budget | CIVIL(A & B Block) | M/s.APARNA CONSTRUCTIONS & ESTATES Pvt Ltd | Aparna Constructions & Estates (P) Ltd. #2nd Floor, Astral Heights, Road No: 1, Banjara Hills, Hyderabad - 500 034 +91 40 2335 2068  +91 40 2335 0329 CIN: U24219TG1996PTC025330 www.aparnaconstructions.com |  |  | 0 | 0 | 0 | 0 | 0 | 0
5 | Block-A & B- Toilet,Balcony,Terrace,Lift Pit & Internal surface OHT | WO NO : ACEPLBLR_CONS \C\177-A\C01753 \ABLR \WO\00020 \1516 | Block-A & B- Toilet,Balcony,Terrace,Lift Pit & Internal surface OHT | NINA WATER PROOFING SYSTEMS PRIVATE LIMITED | Nina Water Proofing Systems Private Limited,B-901 & 902,Floor-9,Plot-1/268, B Wing, Raheja Atlantis,Ganapatrao,Kadam Mar,Mumbai | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | p | p | p |  |  |  | 0 | p
6 | STP & UG Sump Water Proofing Works | WO NO : ACEPLBLR_CONS \C\177-GEN\C01753 \ABLR \WO\00043 \1516 | STP & UG SUMP | NINA WATER PROOFING SYSTEMS PRIVATE LIMITED | Nina Water Proofing Systems Private Limited,B-901 & 902,Floor-9,Plot-1/268, B Wing, Raheja Atlantis,Ganapatrao,Kadam Mar,Mumbai | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | p | p | p |  |  |  | 0 | p
7 | Swimming Pool and Podium Water Proofing Works | WO NO : ACEPLBLR_CONS\C\177-GEN\C01753\ABLR\WO\00020\1516\A0 | Swimming Pool,Water Body & Podium | NINA WATER PROOFING SYSTEMS PRIVATE LIMITED | Nina Water Proofing Systems Private Limited,B-901 & 902,Floor-9,Plot-1/268, B Wing, Raheja Atlantis,Ganapatrao,Kadam Mar,Mumbai | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | p | p | p |  |  |  | 0 | p
8 | UPVC Works -Doors and windows | PO NO: PO-G177/00682/1516 | Block-A & B | M/s. Aparna Enterprises | Aparna Enterprises Limited.Bangalore-UPVC,No.513/1,80 fett road,Opp.,Raghavendra Swamy Temple,Koramangala,Bangalore-560095 |  |  | 0 | 0 | 0 | 0 | 0 | 0
9 | Aluminium Ventilators | PO NO: PO-G177/00694/1516 | Block-A & B | M/s. Aparna Enterprises | Aparna Enterprises Limited.-UPVC,Plot No.1214,Road No.60,Jubilee,Hills-Hyderabad,India |  |  | 0 | 0 | 0 | 0 | 0 | 0
10 | Hardscape Works | WO NO: ACEPLBLR_CONS\K\177-LSW \C02513 \ABL\ WO\ 177\ 0010 | Podium | M/s. Prakruti Creations | M/s. Prakruti Creations, No.25,Prashant Extention,Whitefield,Bangalore-560066 Tel-2845 0702 ,Mail Id -prakruticreationsindia@rediffmail.com | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0
11 | Softscape Works | WO NO: ACEPLBLR_CONS\K\177-LSW \C02565 \ABL\ WO\ 177\ 00127 A0 | Podium & pent House | M/s. Twings | M/s Twings,#1 Keshavareddy complex,1st cross,Kaddadasapura,CV Raman Nagar.Bangalore.Mob: 09845011438 | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0
12 | Club House Interiors Works | WO NO:ACEPLBLR_CONS\177-GEN\C00724\ABL\WO\0016\A1\2016-10-27 | Club House | HYDERABAD INSULATIONS CORPORATION | HYDERABAD INSULATIONS CORPORATION #4, 7th Corss, 3rd Main, LBS Nagar, Vimanapura Post Bangalore – 560 017 E-mail id – ahmed@hicinfrastructure.com www.hicinfrastructure.com AHMED SHARIEFF 9886130533 | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0
12 | Entrance Gate Cladding Works | WO NO: ACEPLBLR_CONS\177-GEN\C00724\ABL\WO\SCO\177\0056\A0 | Club House | HYDERABAD INSULATIONS CORPORATION | HYDERABAD INSULATIONS CORPORATION #4, 7th Corss, 3rd Main, LBS Nagar, Vimanapura Post Bangalore – 560 017 E-mail id – ahmed@hicinfrastructure.com www.hicinfrastructure.com AHMED SHARIEFF 9886130533 | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0
13 | Sitout Glass Railing Works in Typical Floor and Pent House,Pent House Utility Top Glass Roof Covering and pent House Paddle Pool Stair case and MS Covering works | WO NO: ACEPLBLR_CONS\C\177-ZCB\C01676\ABLR\WO\00014\1415\A3\30.03.2015 | Typical Floors and Pent House | VACONS | M/s.Vacons,Terrace Floor,House No.874,Raineo House,Modi Hospital Road,Bangalore. Vishal -9986017022 | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0
14 | Supply of Aliminium Curtain wall glazing System with Pressure Plate and Cover Cap | PO NO: PO-G177/01020/1617 | CLUB HOUSE | CHINIWALAS PVT.LTD | M/s.Chiniwalas Pvt.Ltd.Survey No.104/06,Tiny Industrial Estate Ltd.Pisoli Road,Kondhwa Pune-411048MH,India -Iqbal Chiniwala -09881978600,Mail ID -iqbal@chiniwalas.com, parags@chiniwalas.com | Certified |  | 0 | 0 | 0 | 0 | 0 | 0
15 | Installation of Aliminium Curtain wall glazing System with Pressure Plate and Cover Cap | WO NO: WO-G177/00082/1617 | CLUB HOUSE | ELEGANT ENTERPRISES | M/s Elegant Enterprises,Shop No-1,Trimurthi Gad,Sl.No-15,Opp Lucky plastic,Kondhwa,Ebrahim Chiniwala -9822750075 | Certified |  | 0 | 0 | 0 | 0 | 0 | 0
16 | Supply,Fabrication and Fixing of Façade Access System ( Track & Trolly System ) | WO NO: ACEPLBLR_CONS\D\177-A\C02466\ABL\WO\177\0003\A0 | 19th floor Projection Slab | Cosmos Clean System | #03,7th Cross,Sri Lakshmi,Venkateshwara Nilaya,3rd Floor,Near Telephone Exchange,Muthsandra Road,Varthur,Bengalore-560087, Srinivas Reddy -9243122549,Mail ID- cosmosclean@gmail.com | Certified |  | 0 | 0 | 0 | 0 | 0 | 0
17 | Purchase Order for Supply of Traffic & Parking Appurtenance | WO NO: ACEPLBLR_CONS\J\177-GEN\P00011\ABL\WO\177\0037\A0 | Basements and Podium | Building Control Solutions (I) Pvt.Ltd. | M/s.Building Control Solutions (I) Pvt.Ltd.,#794,12th main,1st Cross,HAL 2nd satge,Indranagar,bangalore-Email: info@controlsol.com,Bhargavi :9980985135,Sarvanan:9980564278 | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0
18 | Building Signages ,Club House signages ,Terrace signages | WO NO: ACEPLBLR_CONS\D\177-GEN\C02641\ABL\SCO\177\0077\A0 | Block-A & B | CYBER SIGNS | M/s Cyber Signs,8-1-402/119,Gulshan Colony,Seven Tombs Road,Shaikpet,Huderabad ,Email: mizafar12@gmail.com | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0
SERVICES
ELECTRICAL WORKS
19 | Internal Electrical Works | WO NO: ABLR\WO\00003\1415 | Block-A & B | CHOWDESHWARI ELECTRICALS & ENGG. WORKS | M/S. CHOWDESHWARI ELECTRICALS & ENGG. WORKS,No. 674, 3rd Stage, 1st Block, 8th 'B'Main, Near Ganesh Temple, Manjunathnagar, Bangalore - 560 010.Rama Chandrappa,Mobile : 9341216706 E-mail : ramengg44@gmail.com | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | 0 |  |  | 0 | 0 | P
20 | WO for external electrical LT side works | WO NO: ABLR\WO\00001\1415 | Block-A & B |  |  | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | 0 |  |  | 0 | 0 | P
21 | Work order for lower and upper penthouses internal electrical works | WO NO: ABL\SCO\177\0052 | Block-A & B |  |  | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | 0 |  |  | 0 | 0 | P
22 | WO for lift shafts internal electrical works | WO NO: ABL\WO\177\0007 | Block-A & B |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | 0 |  |  | 0 | 0 | P
23 | WO for providing 11KV permanant power supply works | WO NO: ABL\WO\177\0011 | Block-A & B |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | 0 |  |  | 0 | 0 | P
24 | Work order for supply and installation of water pumps panle and club house panel works | WO NO: ABL\SCO\177\0049 | Block-A & B |  |  | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | 0 |  |  | 0 | 0 | P
25 | Work order for supply and installation of LT 3phase meters works | WO NO: ABL\SCO\177\0060 | Block-A & B |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | 0 |  |  | 0 | 0 | P
26 | Work order for landscape electrical works | WO NO: ABL\SCO\177\0055 | Podium |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | 0 |  |  | 0 | 0 | P
27 | Work order for club house internal electrical works | WO NO: ABL\SCO\177\0053 | Club House |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | 0 |  |  | 0 | 0 | P
28 | Work order for club house audio and video wiring works | WO NO: ABL\SCO\177\0073 | Club House |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | 0 |  |  | 0 | 0 | P
PLUMBING
29 | Internal plumbing & sanitary works | WO NO: ABLR\WO\00022\1516 | Block-A & B | SAI RAM ENTERPRISES | M/s. Sai Ram Enterprises # 6,“Sri Sai Ram Krupa”,1st cross, 5th main, Balaji Layout, Bangalore 560 094,M. Venkat Reddy -Mobile No: 9845406244 Landline: 040-49524633,080-23516244,E-Mail: mvr.ssrc@yahoo.com. | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | P |  | P | P | P
30 | External Plumbing Works | WO NO: ABLR\WO\00030\1516 | Block-A & B |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | P |  | P | P | P
31 | Construction of rain water recharge pit works | WO NO: ABL\SCO\177\0041 | External |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | P |  | P | P | P
32 | Borewells and muncipal water pipe line works | WO NO: ABL\SCO\177\0047 | External |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | P |  | P | P | P
33 | Basement sub soil drainage works | WO NO: ABL\SCO\177\0048 | Basements |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | P |  | P | P | P
34 | Supply and laying of perforated PVC pipe and excavation works | WO NO: ABL\SCO\177\0065 | External |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | P |  | P | P | P
35 | landscape,OWC,water body,swimming pool and car wash area water supply works | WO NO: ABL\SCO\177\0068 | External |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | P |  | P | P | P
36 | Podium drainage system works | WO NO: ABL\SCO\177\0069 | Podium |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | P |  | P | P | P
37 | Solar hot water piping works | WO NO: ABL\SCO\177\0066 | Terrace |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | P |  | P | P | P
38 | Club house internal and external plumbing works | WO NO: ABL\SCO\177\0071 | CLUB HOUSE |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | P |  | P | P | P
FIRE FIGHTING SYSTEMS
39 | Fire Fighting System Works | WO NO: ABLR\WO\00027\1516 | INTERNAL | DEKARS FIRE & SECURITY SYSTEMS PVT LTD | DEKARS FIRE & SECURITY SYSTEMS PVT LTD,#1-10-212/2, III Floor,Shree Nivas, Street No.6,Ashoknagar, Near Indira Park Hyderabad - 500 020.Mobile: 98480 53546,Tele: 2763 2323/2763 2366, 2763 2388 Fax: 27632323 CIN NO: U31900TG2009PTC062787 E-mail: info@dekars.com | Certified |  | 0 | 0 | 0 | 0 | 0 | 0
40 | FA,PA system integration and fire pumps status indication at security works | WO NO: ABL\SCO\177\0050 | PUMP ROOM |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0
41 | Club house fire fighting works |  | CLUB HOUSE |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0
SWIMMING POOL & WATER BODY WORKS
42 | Supply,Installation,testing and commissioning of 2,58,000 ltr Swimming pool works | WO NO: ABLR\WO\00044\1516\A0 | Swimming Pool | M/s CLEARWATER POOLS PVT LTD | Clearwater Pools Pvt. Ltd. Regd. Office: No:19/1, Ist Floor, Ist Main Road, Kodhandaramapura, Malleswaram , Bangalore - 560 003. E-mail: info@clearwaterpools.in web: www.clearwaterpools.in ,Saravanan -09963448862 | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0
43 | Supply,Installation,testing and commissioning of Water Body works | Yet to Receive | Water Body |  |  | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P |  | P | P | P | P
LANDSCAPE IRRIGATION WORKS
44 | Landscape irrigation works | WO NO: ABL\WO\177\0036 | Podium | KAVERI IRRIGATIONS | Gomukhi point,102,Sangunagar, EB complex back side,Collectorate post,Erode-District, PIN -638011,TAMILNADU ,India. Tel/fax: +91-424-2273032,2273033: Mobile: +91-94433-60700 Email: ssivam5@yahoo.com | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0
VENTILATION SYSTEM
45 | Supply,Installation,Testing & Commissioning of STP Ventilation System | PO NO: PO-G177/00922/1617 | STP | TAP ENGINEERING. | Tap Engineering,Bangalore.NO-296,Ground Floor,West of Chord Rpad,2nd Stage,2nd Phase.Bangalore-560086KA,India,Contact Person-B Sasi Kumar,Mob: 9342502194,E Mail: sasi@tapengineering.com | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
46 | Supply,Installation,Testing & Commissioning of Basement Ventilation System | PO NO: PO-G177/00920/1617 | BASEMENT |  |  | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
WTP & STP TREATMENT
47 | Supply,Installation,Testing & Commissioning of 120KLD WTP | PO NO: PO-G177/00915/1617 | PUMP ROOM | AMZON ENVIROTECH PVT.LTD | M/S.AMZON ENVIROTECH PVT.LTD,#19,Pottery Road,Cooke Town,Bangalore-560005KA,India-Contact Person-N Kumara Swamy-Mob: 9845151245,E Mail-admin@amazonenviro.com |  |  | 0 | 0 | 0 | 0 | 0 | 0
48 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
LIFT WORKS
49 | Supply,Installation,Erection,Testing and Handing over of 4 nos od passenger lifts and 2 nos of goods lifts | PO NO: PO-G-177/00693/1516 & WO-NO: G177/00042/1516 | Block-A & B | MITSUBISHI ELEVATOR INDIA PVT.LTD | M/s. MITSUBISHI ELEVATOR INDIA PVT.LTD.Bangalore,The Estate,201,2nd Floor,121,Dickenson Road,Bangalore-560042KA,India,Contact Person-S.M.Rajan,Mob: 9972572448,E Mail-rajan.s@mitsubishielevator.in | Certified |  | 0 | 0 | 0 | 0 | 0 | 0
GAS RETICULATION SYSTEM
50 | Supply and installation, testing and commissioning of Gas Reticulated System Works | WO NO: ACEPLBLR_CONS\177-GEN\S01873\ABLR\WO\00029\1516\A0\2015-10-14 | Block-A & B | Futuristic Gas Systems Pvt Ltd, Bangalore | Futuristic Gas Systems Pvt Ltd, Bangalore,Darshan Mokal, Marketing Manager, Futuristic Gas Systems Pvt.Ltd, Mobile No :- 09930383923 Email: marketing@futuristicgases.com. |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | P | P | P | P | P | P | P | P | P
51 | Gas Reticulation system | WO NO: ACEPLBLR_ CONS/I/177-GEN/S00221/ABL/SCO/177/0067/A0 | Block-A & B | M/s EMINENT GAS TECHNOLOGIES PVT LTD | Eminent Gas Technologies Pvt Ltd 29, Haria Industrial estate, Off LBS Marg,Behind capitol Hotel, Majiwada, Thane Maharashtra, India 400601 Skype: mskishore65 Ph: 91 22 21736346 Mob: +91 9987244210 Visit Us; www.eminentgas.in OR www.indiamart.com/eminent-gas |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | P | P | P | P | P | P |  | P
PADDLE POOL WORKS
52 | Supply and installation, testing and commissioning of Paddle Pools at Pent house |  | Block-A & B | M/S. SmartPools (International) Pvt Ltd. | SmartPools(International) Private Limited,SmartPools House, 35/1B, Sathnur Road, Next to country club, Yelahanka Bangalore-560 063. Ph # 080-65310002/03 E-mail: accounts@smartpools.com.my,Contact person: Anil.H.S -Mob:+91-9972244521 P: +91 80 65310002/03 | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P |  | P | P | P | P
SOLAR FENCING & BOOM BARRIER
53 | Supply and installation of Renewable Energy Devices and Spares for Solar Fencing for Elina-Blr Project | WO NO: ACEPLBLR_ CONS/J/177-GEN/S00037/ABL/WO/177/0034/A0 | Compound wall | ALLIANCE SECURITY SYSTEMS | M/S. ALLIANCE SECURITY SYSTEMS,#301,Kaizen Imperial Heights,D.No-6-3-1219/7,Str no-,Secunderabad,Contact person-V. Vijaya Bhasker-9848124717 | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | 0 | P | P | P | P | P
54 | Supply,Installation,Testing & Commissioning of Automatic Hydraulic Boom Barrier | WO NO: ACEPLBLR_ CONS/J/177-GEN/S00037/ABL/SCO/177/0043/A0 | Entry & Exit Ramp | ALLIANCE SECURITY SYSTEMS | M/S. ALLIANCE SECURITY SYSTEMS,#301,Kaizen Imperial Heights,D.No-6-3-1219/7,Str no-,Secunderabad,Contact person-V. Vijaya Bhasker-9848124717 | Yet to Submit |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P | 0 | P | P | P | P | P
CC TV
55 | Supply,Installation,Testing & Commissioning of CCTV works for Elina Project | WO NO: ACEPLBLR_ CONS/J/177-GEN/S02172/ABL/WO\177/0040/A0 | Block-A & B | SECURITY ALERT SYSTEMS | M/S. SECURITY ALERT SYSTEMS,H.No:9F,Phase-1,Janapriya Nagar,Miyapur,Hyderabad,Email:ravi@securityalertsystems.co.in,RAVI KUMAR.B. Mob: 040-48507718,9989393850 |  |  | 0 | 0 | 0 | 0 | 0 | 0
VRV -NON-VRV A.c's AT CLUB HOUSE
56 | Supply Installation & Commissioning of Copper Piping for VRV-NON VRV A.c's Low side works at Elina Club House | PO NO: PO-G177/01044/1617 & WO NO:WO-G177\00084\1617 | CLUB HOUSE | INTELLIMECH SYSTEMS | M/S INTELLIMECH SYSTEMS, | Certified |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
SAUNA
57 | Supply Installation & Commissioning of Sauna cabin for Gents Spa and Ladies Spa at Elina Club House | PO NO: PO-G177/01118/1617 | CLUB HOUSE | LINCO BEAUTY & SLIMMING EQUIPMENT PVT.LTD | M/s.LINCO BEAUTY & SLIMMING EQUIPMENT PVT.LTD,Plot No.92,Mahesh Nagar Opp.ETDC,ECIL Post,Hyderabad,India,Contact Person-Mr.Gangadharan Sre,Mob No: 9390031318 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P | P | P |  | P | P | P | P

## Check List
PROJECT : APARNA ELINA.BANGALORE
OWNER:M/S APARNA CONSTRUCTIONS AND ESTATES PVT.LTD
PACKAGE:
NAME OF THE WORK:
VENDOR NAME:
PURCHAGE ORDER NO:
SL.NO | DESCRIPTION | YES | NO | N/A | REMARKS
1 | P.O/W.O COPY
2 | SCHEMATIC DIAGRAM
3 | AS-BUILT DRAWINGS
4 | CHECK LIST
5 | TESTING & COMMISSIONING REPORT
6 | OPERATION & MAINTENANCE MANUALS(DO'S & DONT'S CATALOGUES)
7 | LIST OF EQUIPMENTS & CERTIFICATES
8 | FACTORY TEST CERTIFICATES
9 | WARRANTEES & GUARANTEES/DLP
10 | INVENTORY / SPARE LIST
11 | TRAINING SCHEDULE FOR HANDINGOVER
12 | CONTACT LIST
The Above was checked & found to be as per the contract conditions & specifications
HANDING OVER BY WITNESSED BY |  |  |  | TAKEN OVER BY
CONTRACTOR ACEPL |  |  |  | APMS

## Materials Details
APARNA ELINA.BANGALORE
SL.NO | DESCRIPTION OF MATERIALS | MAKE | USED LOCATION | REMARKS
PAINTING WORK
| Exterior Emulsion ACE, Shade: Crystal Peak, Code: L105 | Asian | Basement #01& 2 and duct internal Painting Purpose
| Exterior Emulsion ACE, Shade: Grey, Code: 8302 | Asian | Basement #01& 2 1.0 mt height Painting Purpose
| External Texture, Swirl Tex, Apex Duracast, Asian | Asian | Tower External Painting
| Exterior paint, Apex Ultima, Shade: Crystal Peak, Code: L105, Make: Asian | Asian | Tower External Painting
| External Wall Putty - Super Fine |  | Lobby ceiling,walls and stair case painting purpose
| Exterior Primer - Water Based |  | Lobby ceiling,walls,stair case and ducts painting purpose
| External Texture, Professional Finetex, Code: 1028, Make: Asian | Asian | Block-A & B Lift lobby 1.0 mt Painting purpose
| Internal Emulsion, Premium, Shade: Iced Silver, Code: 8236, Make: Asian | Asian | Lobby ceiling,walls and stair case painting purpose
| Internal Emulsion, Premium, Shade: Silica Dream, Code: 8235, Make: Asian | Asian | Lobby Walls up to 1.0 Mt height painting purpose
| Exterior Primer, CT-Under, Make: SKK, 25.5 kgs | SKK | Ground and First floor External Painting
| Exterior Texture, Sand Elegnate, Code: 012, Make: SKK | SKK | Ground and First floor External Painting
| Exterior Top Coat, Aqua Clear Ace Si, Make: SKK | SKK | Ground and First floor External Painting
| Internal wall putty - Acrylic | Acrylic | Flat Internal Painting purpose
| Interior Primer - Water Based | Asian | Flat Internal Painting purpose
| Internal Emulsion, Premium, Unolnt | Asian | Flat Internal Painting purpose
| Enamel paint, Crystal Peak, Code: L105 | Asian | All MS works Painting Except Stair case railing
| Enamel Paint Black Color | Asian | Stair Case Railing painting
TILES WORK
TYPICAL FLOOR
| Athangudi Tile, Size: 250x125x18mm |  | Foyer Skirting
| Athangudi Tile, Size: 250x250x20mm |  | Foyer Polishing
| Vitrified Tile, Flr, Aurum White, 'Nitco', 800x800mm, 1.92Sqm/box | Nitco | Living/Dining /Kitchen & Bedroom Flooring and Skirting
| Vitrified Tile, Sydney Cemento, 'Kajaria', 600x1200mm, 1.44Sqm/box | Kajaria | Toilet Flooring and Dado
| Ceramic Tile, Flr, 393101, 'Motto',300x300mm, 0.81Sqm/box | Motto | Powder Toilet Flooring and Dado
| Ceramic Tile, Wall, 393101, 'Motto',300x900mm, 1.08Sqm/box | Motto | Powder Toilet Dado
| Ceramic Tile, Wall, 393201, 'Motto',300x900mm, 1.08Sqm/box | Motto | Powder Toilet Dado
| Vitrified Tile, Wall, Techno Flr -HD 1025 B, 'Italica', 600x600mm, 1.44Sqm/box | Italica | M Toilet Heighliter
| Ceramic Tile, Wall,97004, 'Motto', 300x600mm, 1.44Sqm/box | Motto | Kids Toilet Heighliter
| Vitrified Tile, Wall,Estilo Fog - Design, 'Nitco', 600x600mm, 1.44Sqm/box | Nitco | Guest toilet Heighliter
| Vitrified Tile, Wall,Estilo Fog - Plain, 'Nitco', 600x600mm, 1.44Sqm/box | Nitco | Guest toilet Heighliter
| Ceramic Tile, Flr, Titan Beige, 'Asian', 397x397mm, 0.946sqm/box | Asian | Ser Room ,Ser Toilet and Utility Floor and Dado
| Ceramic Tile, Flr, Wooden Pattern Castilla Brown, 'Italica', 600x600mm 1.44 sqm/box | Italica | Balcony Flooring and Skirting
| Vitrified Tile, Flr, Emperador Gris, 'Simpolo', 600x1200mm, 1.44Sqm/box | Simpolo | Lift Lobby Flooring
| Vitrified Tile, Flr, Emperador Nero,'Simpolo', 600x1200mm, 1.44Sqm/box | Simpolo | Lift Lobby Flooring,Skirting and Lift Clading
| Vitrified Tile, Boston Wenge, Qutone, 600x1200mm, 1.44 Sqm/Box | Qutone | Lobby Sitout Flooring and Skirting
| Wooden Flooring, AC4, Action Tesa | Action Tesa | Master Bed room Flooring
PENT HOUSE
| Vitrified Tile, Flr,Kohinoor White,'NCL,'1000x1000mm, 2.00Sqm/Box | NCL | Living/Dining /Kitchen & Bedroom Flooring and Skirting
| Vitrified Tile, Mapple Wood, Simpolo, 600X600mm, 0.72 sqm/Box | Simpolo | Pedalpool area flooring and dado
| Vitrified Tile, Concrete Natural, Simpolo, 600X1200mm, 1.44 sqm/Box | Simpolo | Balcony Flooring and Skirting
| Vitrified Tile, Flr, Aurum White, 'Nitco', 800x800mm, 1.92Sqm/box | Nitco | Living/Dining /Kitchen & Bedroom Flooring and Skirting
Total Floring
| Vitrified Tile, Neo Crema, Qutone, 600X600mm, 1.44 sqm/Box | Qutone
| Vitrified Tile, Urban Gris, Qutone, 600X600mm, 1.44 sqm/Box | Qutone
| Vitrified Tile, Jupiter grey, Simpolo, 600X600mm, 1.44 Sqm/Box | Simpolo
| Vitrified Tile, GC-6214F, GLB, 600X600mm, 0.36 sqm/Box | GLB
Toilet Dado
| Ceramic Tile, Wall, 24031 LT, Motto, 600X300mm, 1.44 Sqm/Box | Motto
| Vitrified Tile, Antica Choco, Qutone, 450X900mm, 1.62 sqm/Box | Qutone
| Vitrified Tile, Antica Gris, Qutone, 450X900mm, 1.62 sqm/Box | Qutone
| Vitrified Tile, City Bianco, Qutone,900X450mm, 1.62 Sqm/Box | Qutone
| Vitrified Tile, Iron Wood White, Simpolo, 195X1200mm, 1.44 sqm/Box | Simpolo
| Vitrified Tile, Marmos Beige, Qutone, 300X1200mm, 2.16 sqm/Box | Qutone
| Vitrified Tile, Marmos Olive, Qutone, 300X1200mm, 2.16 sqm/Box | Qutone
| Vitrified Tile, Montana Black, 'Simpolo', 600x600mm, 1.44 Sqm/box | Simpolo
| Vitrified Tile, Slate Nero, Simpolo, 195X1200mm, 1.44 sqm/Box | Simpolo
CLUB HOUSE
| Ceramic Tile, Irish Block'O', Qutone, 300X600mm, 1.44 Sqm/Box | Qutone
| Vitrified Tile, City Bianco, Qutone,900X450mm, 1.62 Sqm/Box | Qutone
| Vitrified Tile, City Gris Matt, Qutone,450X900mm, 1.62 Sqm/Box | Qutone
| Vitrified Tile, GC6019(Dark), Genese,600X600mm, 0.36 Sqm/Box | Genese
| Vitrified Tile, GPRT8055 PL222FS, Srushti,800X800mm, 1.92 Sqm/Box | Srushti
| Vitrified Tile, King Wood Moka, Simpolo,195X1200mm, 1.40 Sqm/Box | Simpolo
| Vitrified Tile, Logos Beige, Qutone,1200X600mm, 1.44 Sqm/Box | Qutone
| Vitrified Tile, Pulpise Beige, Simpolo,1200X600mm, 1.44 Sqm/Box | Simpolo
| Vitrified Tile, Trans Beige Matt, Qutone, 450X900mm, 1.62 Sqm/Box | Qutone
| Vitrified Tile, Vanilla Nero, Qutone, 600X600mm, 1.44 Sqm/Box | Qutone
| Vitrified Tile,Logos Antarctica, Qutone, 600X1200mm, 1.44 Sqm/Box | Qutone