## 2015 PM SCHEDULE (hidden)
Aparna Property Management Services Pvt Ltd
Planned Preventive Maintenance Schedule for the year - 2015
Categeory | Job Description | PM Frequency |  | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Electrical | Transformers - 4 Nos | yearly | bar: May 19; November 45
| 33 KV VCB & CTPT Panels - 13 Nos | yearly | bar: June 24; December 49
| LT Panels - ACB's - 4 Nos | yearly | bar: May 19; November 45
| DG Sets - 250 KVA - 16 Nos | Quarterly
| Main PCC Panels - 8 Nos | Annually
| Earth Pits | Half Yearly | bar: February 6; May 19; August 32; November 45
| CC Cameras - 40 Nos | Quarterly | bar: April 16
| Boom Barriers - 8 Nos | Quarterly | bar: April 15; July 28; October 40
| Solar Fencing | Half Yearly
| Sub cellar Ventillation System | yearly | bar: June 24; December 49
| Lightning Arrestor -7 Nos | yearly | bar: December 49
| Club House Panel - 2 Nos | yearly
| Fire Panels - 14 Nos | Quarterly | bar: March 10; June 24; September 36; December 49
| STP Panel - 2 Nos | Quarterly | bar: April 15; July 28; October 40; December 49
| WTP Panel - 1 No | Quarterly | bar: March 10; June 24; September 36; December 49
| Common Supply Panels - 7 Nos | Quarterly | bar: March 10
| Distribution Boards - 14 Nos | Quarterly | bar: March 10
| Bus Ducts - All flats | Annually | bar: January 1
| Land Scape Lighting panels -7 Nos | Quarterly | bar: March 14; June 27; September 39; December 52
| Corridor & Stair case Lighting | Quarterly | bar: March 14; June 27; September 39; December 52
| Cellar & Sub cellar Lighting | Quarterly | bar: February 9; May 23; August 35; December 49
| Irrigation Pumps - 14 Nos | Quarterly | bar: March 10; June 24; September 36; December 49
| Water Body Pumps | Quarterly | bar: March 10; June 24; September 36; December 49
| Mist Fountain Pumps | Quarterly | bar: March 10; June 24; September 36; December 49
| Storm Water Pumps - 12 Nos | Quarterly | bar: March 10; June 24; September 36; December 49
STP | STP -Hydropneumatic pumps - 4 Nos | Annually | bar: March 13
| STP- Air Blowers - 3 Nos | Half yearly | bar: January 3; July 30
| STP- Filter feed pumps - 2 Nos | Quarterly | bar: January 2; April 16; July 29; October 41
| STP- Raw sewage pumps - 2 Nos | Quarterly | bar: January 2; April 16; July 29; October 41
| STP - Sledge Transfer Pumps - 2 Nos | Quarterly | bar: January 2; April 16; July 29; October 41
| STP - Screw pumps | Quarterly | bar: January 2; April 16; July 29; October 41
| STP- Filters - 4 Nos | Annually | bar: January 2
| UV System | Quarterly | bar: January 2; April 16; July 29; October 41
| STP- De-watering pump - 1 Nos | Quarterly | bar: January 2; April 16; July 29; October 41
| STP- AHU | Quarterly | bar: January 2; April 16; July 29; October 41
WTP | WTP -Hydropneumatic pumps - 4 Nos | Annually | bar: April 15
| WTP - Filters - 2 Nos | Annually | bar: April 15
| WTP - Filter feed pumps - 2 Nos | Quarterly | bar: February 6; May 20; August 33; November 46
| WTP - Rain Water Pump -1 Nos | Quarterly | bar: February 6; May 20; August 33; November 46
| WTP -Borewells - 4 Nos | Quarterly | bar: February 6; May 20; August 33; November 46
| WTP - De-Watering Pump - 1 Nos | Quarterly | bar: February 6; May 20; August 33; November 46
Fire & safety | Jockey Pumps - 14 Nos | Quarterly | bar: March 11; June 25; September 37; December 50
| Main Pumps - 14 Nos | Quarterly | bar: March 11; June 25; September 37; December 50
| DG Engine Pumps - 14 Nos | Quarterly | bar: March 11; June 25; September 37; December 50
| Podium Hydrants | Monthiy | bar: January 2; February 7; March 11; April 16; May 20; June 25; July 29; August 33; September 37; October 41; November 46; December 50
| Over Head Tanks Cleaning | Half Yearly | bar: February 7; August 33
| Fire Alarms & PA System | Monthly | bar: January 5; February 9; March 14; April 18; May 23; June 27; July 31; August 35; September 39; October 44; November 48; December 52
Sumps & Tanks Cleaning | WTP -Raw Water Sump - 1 Nos | Half Yearly | bar: June 24; December 49
| WTP -MCH Water Sump -2 Nos | Half Yearly | bar: June 24; December 49
| WTP -Final tank - 1 Nos | Half Yearly | bar: June 24; December 49
| STP - Pre-filtration tank | Quarterly | bar: January 1; February 6; March 10; April 15; May 19; June 24; July 28; August 32; September 36; October 40; November 45; December 49
| STP- Final Tank | Quarterly | bar: March 10; June 24; September 36; December 49
| Rain Water Sump -1 nos | Annually | bar: January 1; April 15; July 28; October 40; December 49
| Storm Water Sump - 14 Nos | Annually | 70 | bar: January 1; July 28
| Fire Sumps -14 Nos | Annually | bar: January 1; April 15; July 28; October 40
| Over Head Tanks - 14 Nos | Annually | bar: January 1; April 15; July 28; October 40
Plumbing | Irrigation sprinkler system | Half yearly | bar: January 1; July 28
| Garden area chambers | Half Yearly | bar: June 24; December 49
| Cellar & sub cellar Drain lines | Half Yearly | bar: May 19; November 45
| Car wash area Drain Chambers | Half Yearly | bar: June 24; December 49
| PRV 's | Annually | bar: May 19; November 45
| Podium drain lines | Half Yearly | bar: June 24; November 45
| Water Bodies - 3 Nos | Quarterly | bar: March 10; June 24; September 36; December 49
[36 empty] | 4 | 5 | 20

## 2019 PM SCHEDULE
Aparna Property Management Services Pvt Ltd
Planned Preventive Maintenance Schedule for the year - 2018
Categeory | Job Description | PM Frequency | Remarks | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Electrical | Transformers - 4 Nos | Annually | Before Monsoon | bar: May 19; November 45
| 33 KV VCB & CTPT Panels - 13 Nos | Annually | Before Monsoon | bar: May 19; December 49
| LT Panels - ACB's - 4 Nos | Annually | Before Monsoon | bar: May 19
| DG Sets - 250 KVA - 16 Nos | Monthly(AMC) | bar: January 2; February 7; March 11; April 16; May 20; June 25; July 29; August 33; September 37; October 41; November 46; December 50
| Main PCC Panels - 8 Nos | Annually
| Earth Pits | Half yearly | Garden cutting will be done in march Month, so work should be done at that time | bar: March 14; November 45
| CC Cameras - 40 Nos | Quarterly | bar: March 11; June 25; October 41; December 52
| Boom Barriers - 8 Nos | Quarterly | bar: March 10; June 24; October 40; December 51
| Solar Fencing | Monthly(AMC) | Security wise, it is important for that month maintenace will be done | bar: January 5; February 9; March 14; April 18; May 23; June 27; July 31; August 35; September 39; October 44; November 48; December 52
| Sub cellar Ventillation System | Annually | bar: June 24
| Lightning Arrestor -7 Nos | Annually | bar: March 14
| Club House Panel - 2 Nos | Half yearly | bar: February 7; August 33
| Fire Panels - 14 Nos | Annually | bar: May 23
| STP Panel - 2 Nos | Quarterly | bar: March 14; June 27; September 39; December 52
| WTP Panel - 1 No | Quarterly | bar: March 10; June 24; September 36; December 49
| Common Supply Panels - 7 Nos | Half yearly | bar: March 11; June 25; September 37; December 50
| Land Scape Lighting panels -7 Nos | Half yearly | bar: March 14; October 40
| Irrigation starters - 14 Nos | Half yearly | bar: June 24; December 49
| Water Body Starters | Half yearly | bar: March 10; June 24; September 36; December 49
| Storm Water Staters- 12 Nos | Half yearly | bar: February 9; August 35
| Borewells Starters - 9 Nos | Quarterly | bar: March 10; June 24; September 36; December 49
STP | STP -Hydropneumatic pumps - 4 Nos | Monthly(AMC) | bar: January 5; February 9; March 14; April 18; May 23; June 27; July 31; August 35; September 39; October 44; November 48; December 52
| STP- Air Blowers - 3 Nos | Half yearly | bar: June 25; December 50
| STP- Filter feed pumps - 2 Nos | Quarterly | bar: January 2; April 16; July 29; October 41
| STP- Raw sewage pumps - 2 Nos | Half yearly | bar: April 16; October 41
| STP - Sludge Transfer Pumps - 2 Nos | Quarterly | bar: January 2; April 16; July 29; October 41
| STP - Feed Pumps | Half Yearly | bar: June 24; December 49
| STP- Filters - 4 Nos | Half yearly | bar: January 2
| STP- De-watering pump - 1 Nos | Half yearly | bar: April 18; October 41
| STP- AHU | Half yearly | bar: April 18; October 41
| STP- Centrifuge | Half yearly | bar: April 15; October 40
WTP | WTP -Hydropneumatic pumps - 4 Nos | Monthly(AMC) | bar: January 5; February 9; March 14; April 18; May 23; June 27; July 31; August 35; September 39; October 44; November 48; December 52
| WTP - Filters - 2 Nos | Annually | bar: April 15
| WTP - Filter feed pumps - 3 Nos | Half Yearly | bar: February 6; August 33; November 46
| WTP - Rain Water Pump -1 Nos | Annually | bar: February 7
| WTP - De-Watering Pump - 1 Nos | Half Yearly | bar: February 6; August 33; November 46
Fire & safety | Jockey Pumps - 14 Nos | Monthly(AMC) | bar: January 5; February 9; March 14; April 18; May 23; June 27; July 31; August 35; September 39; October 44; November 48; December 52
| Main Pumps - 14 Nos | Anually | bar: June 25
| DG Engine Pumps - 14 Nos | Monthly(AMC) | bar: May 20; November 46
| Fire Alarms & PA System | Quaterly | bar: February 9; May 23; August 35
Sumps & Tanks Cleaning | WTP -Raw Water Sump - 2 Nos | Quarterly | bar: February 8; May 22; August 34; November 47
| WTP -Treated Water Sump -2 Nos | Quarterly | bar: March 10; June 24; September 36; December 49
| STP - Pre-filtration tank | Alternate Months | bar: January 1; March 10; May 19; July 28; September 36; November 45
| STP- Final Tank | As Require | bar: March 10; June 24; September 36; December 49
| Rain Water Sump -1 nos | Annually | Before Monsoon | bar: April 18
| Storm Water Sump - 12 Nos | Annually | Before Monsoon | bar: April 18
| Fire Sumps -14 Nos | Annually | In rainy Season there is no need of water(June-July) | bar: June 25 to July 29
Plumbing | Irrigation sprinkler system | Half yearly | bar: May 23; November 48
| Garden area chambers | Half yearly | Garden cutting will be done in march Month, so work should be done at that time | bar: June 24; December 49
| PRV 's | Annually | bar: April 18
| Water Body Pumps | Half yearly | bar: March 14; September 39
| Storm Water Pumps - 12 Nos | Half yearly | bar: April 15; October 40

## JAN
Planned Preventive Maintenance for Month of Jan
S.No. | Job Description | Assign to
1 | DG Sets - 250 KVA - 16 Nos
2 | Solar Fencing
3 | Bus Duct Raiser
4 | STP -Hydropneumatic pumps - 4 Nos
5 | STP - Filter Feed Pumps - 2 Nos
6 | STP - Sludge Transfor Pumps - 2 Nos
7 | STP - Filters - 4 Nos
8 | WTP -Hydropneumatic pumps - 4 Nos
9 | Jockey Pumps - 14 Nos
10 | Podium Hydrants
11 | STP - Pre-filtration tank
Remarks:

## FEB
Planned Preventive Maintenance for Month of Feb
S.No. | Job Description | Assign to
1 | DG Sets - 250 KVA - 16 Nos
2 | Solar Fencing
3 | Club House Panel - 2 Nos
4 | Strom Water Staters - 12 Nos
5 | STP -Hydropneumatic pumps - 4 Nos
6 | WTP -Hydropneumatic pumps - 4 Nos
7 | WTP - Filter Feed Pumps - 3 Nos
8 | WTP - Rain Water Pump - 1 Nos
9 | WTP - De-watering Pump -1 Nos
10 | Jockey Pumps - 14 Nos
11 | Podium Hydrants
12 | Fire Alarms & PA System
13 | WTP -Raw Water Sump - 2 Nos
Remarks:

## MAR
Planned Preventive Maintenance for Month of March
S.No. | Job Description | Assign to
1 | DG Sets - 250 KVA - 16 Nos
2 | Earth Pits
5 | Solar Fencing
6 | Lightning Arrestor - 7 Nos
7 | STP - Panel -2 Nos
8 | WTP - Panel -1 Nos
9 | Common Supply Panels - 7 Nos
10 | Land Scape Lightning Panels - 7 Nos
11 | Irrigation Staters - 14 Nos
12 | Water Body Staters
13 | Borewell Staters - 9 Nos
14 | STP -Hydropneumatic pumps - 4 Nos
15 | WTP -Hydropneumatic pumps - 4 Nos
16 | Jockey Pumps - 14 Nos
17 | Podium Hydrants
18 | Water Body Pump
Remarks:

## APL
Planned Preventive Maintenance for Month of April
S.No. | Job Description | Assign to
1 | DG Sets - 250 KVA - 16 Nos
2 | Solar Fencing
3 | STP - Hydropneumatic pumps - 4 Nos
4 | STP - Filter Feeder Pumps -2 Nos
5 | STP - Raw Water sweage Pumps - 2 Nos
6 | STP - Sludge Tranfer Pumps - 2 Nos
7 | STP - DE-watering Pumps - 1 Nos
8 | STP - AHU
9 | STP - Centrifuge
10 | WTP - Hydropneumatic pumps - 4 Nos
11 | WTP - Filters - 2 Nos
12 | Jockey Pumps - 14 Nos
13 | Podium Hydrants
14 | PRV's
Remarks:

## MAY
Planned Preventive Maintenance for Month of May
S.No. | Job Description | Assign to
1 | Transformers - 4 Nos
2 | 33 KV VCB & CTPT Panels - 13 Nos
3 | LT Panels - ACB's - 4 Nos
4 | DG Sets - 250 KVA - 16 Nos
5 | Solar Fencing
6 | Fire Panels - 14 Nos
7 | STP -Hydropneumatic pumps - 4 Nos
8 | WTP -Hydropneumatic pumps - 4 Nos
9 | Jockey Pumps - 14 Nos
10 | DG Engine Pumps - 14 Nos
11 | Podium Hydrants
12 | Fire Alarms & PA System
13 | WTP -Raw Water Sump - 2 Nos
14 | STP - Pre-filtration tank
15 | Irrigation sprinkler system
16 | Cellar & sub cellar Drain lines
Remarks:

## June
Planned Preventive Maintenance for Month of June
S.No. | Job Description | Assign to
1 | DG Sets - 250 KVA - 16 Nos
2 | CC Cameras - 40 Nos
3 | Boom Barriers - 8 Nos
4 | Solar Fencing
5 | Sub cellar Ventillation System
6 | STP Panel - 2 Nos
7 | WTP Panel - 1 No
8 | Common Supply Panels - 7 Nos
9 | Irrigation starters - 14 Nos
10 | Water Body Starters
11 | Mist Fountain Starters
12 | Borewells Starters - 9 Nos
13 | STP -Hydropneumatic pumps - 4 Nos
14 | STP- Air Blowers - 3 Nos
15 | STP - Feed Pumps
16 | WTP -Hydropneumatic pumps - 4 Nos
17 | Jockey Pumps - 14 Nos
18 | Main Pumps - 14 Nos
19 | Podium Hydrants
20 | WTP -Treated Water Sump -2 Nos
21 | STP- Final Tank
22 | Fire Sumps -14 Nos
23 | Fire & Irrigation Over Head Tanks - 14 Nos
24 | Garden area chambers
25 | Podium drain lines

## July
Planned Preventive Maintenance for Month of July
S.No. | Job Description | Assign to
1 | DG Sets - 250 KVA - 16 Nos
2 | Solar Fencing
3 | STP -Hydropneumatic pumps - 4 Nos
4 | STP - Filter Feeder Pumps -2 Nos
5 | STP - Sludge Tranfer Pumps - 2 Nos
6 | WTP -Hydropneumatic pumps - 3 Nos
7 | Jockey Pumps - 14 Nos
8 | Podium Hydrants
9 | STP - Pre-filtration tank
10 | Fire Sumps -14 Nos
11 | Fire & Irrigation Over Head Tanks - 14 Nos
Remarks:

## August
Planned Preventive Maintenance for Month of August
S.No. | Job Description | Assign to
1 | DG Sets - 250 KVA - 16 Nos
2 | Solar Fencing
3 | Club House Panel - 2 Nos
4 | Storm Water Staters- 12 Nos
5 | STP -Hydropneumatic pumps - 4 Nos
6 | WTP -Hydropneumatic pumps - 4 Nos
7 | WTP - Filter feed pumps - 3 Nos
8 | WTP - De-Watering Pump - 1 Nos
9 | Jockey Pumps - 14 Nos
10 | Podium Hydrants
11 | Fire Alarms & PA System
12 | WTP -Raw Water Sump - 2 Nos
Remarks:

## September
Planned Preventive Maintenance for Month of September
S.No. | Job Description | Assign to | Schedule date
1 | DG Sets - 250 KVA - 16 Nos | Electrical
2 | Earth Pits | Electrical | 08.09.2018
3 | CC - Cameras - 40 Nos | Electrical
4 | Boom Barriers - 8 Nos | Electrical
5 | Solar Fencing | AMC
6 | Lightning Arrestor - 7 Nos | Electrical | 11.09.2018
7 | STP - Panel -2 Nos | Electrical | 13.09.2018
8 | WTP - Panel -1 Nos | Electrical | 13.09.2018
9 | Common Supply Panels - 7 Nos | Electrical | 15.09.2018
10 | Land Scape Lightning Panels - 7 Nos | Electrical | 18.09.2018
11 | Irrigation Staters - 14 Nos | Electrical | 20.09.2018
12 | Water Body Staters | Electrical | 22.09.2018
14 | Borewell Staters - 9 Nos | Electrical | 25.09.2018
15 | STP -Hydropneumatic pumps - 4 Nos | Revolve | Revolve
16 | WTP -Hydropneumatic pumps - 4 Nos | Revolve | Revolve
17 | Jockey Pumps - 14 Nos | Revolve | Revolve
18 | Podium Hydrants | F & S | F & S
19 | WTP - Treated Water Sumps - 2 Nos | Plumbing | 10.09.2018
20 | STP - Pre-fliteration Tank | Plumbing | 12.09.2018
21 | STP- Final Tank | Plumbing | 14.09.2018
22 | Water Body Pump | Plumbing | 16.09.2018
Remarks:

## October
Planned Preventive Maintenance for Month of October
Sl No | Job Description | PM Frequency
1 | DG Sets - 250 KVA - 16 Nos | AMC
2 | CC Cameras - 40 Nos
3 | Boom Barriers - 8 Nos
4 | Solar Fencing | AMC
5 | Land Scape Lighting panels -7 Nos | Completed in Sept
6 | STP -Hydropneumatic pumps - 4 Nos | AMC
7 | STP- Filter feed pumps - 4 Nos
8 | STP- Raw sewage pumps - 2 Nos
9 | STP - Sludge Transfer Pumps - 2 Nos
10 | STP- De-watering pump - 1 Nos
11 | STP- AHU
12 | STP- Centrifuge
13 | WTP -Hydropneumatic pumps - 4 Nos | AMC
14 | Jockey Pumps - 14 Nos
15 | Podium Hydrants
16 | Mist Fountain Pumps
17 | Storm Water Pumps - 12 Nos
Remarks:

## November
Planned Preventive Maintenance for Month of November
SR.NO | Job Description | Assign to
1 | Transformers - 4 Nos
2 | DG Sets - 250 KVA - 16 Nos
3 | Earth Pits
4 | Solar Fencing | AMC
5 | STP -Hydropneumatic pumps - 4 Nos | AMC
6 | WTP -Hydropneumatic pumps - 4 Nos | AMC
7 | WTP - Filter feed pumps - 3 Nos
8 | WTP - De-Watering Pump - 1 Nos
9 | Jockey Pumps - 14 Nos
10 | DG Engine Pumps - 14 Nos
11 | Podium Hydrants
12 | WTP -Raw Water Sump - 2 Nos
13 | STP - Pre-filtration tank
14 | Irrigation sprinkler system
Remarks:
ca

## December
Planned Preventive Maintenance for Month of December
Sl no | Job Description | Assigned to
1 | 33 KV VCB & CTPT Panels - 13 Nos
2 | DG Sets - 250 KVA - 16 Nos
3 | CC Cameras - 40 Nos
4 | Boom Barriers - 8 Nos
5 | Solar Fencing
6 | STP Panel - 2 Nos
7 | WTP Panel - 1 No
8 | Common Supply Panels - 7 Nos
9 | Irrigation starters - 14 Nos
10 | Water Body Starters
11 | Mist Fountain Starters
12 | Borewells Starters - 9 Nos
13 | STP -Hydropneumatic pumps - 4 Nos
14 | STP- Air Blowers - 3 Nos
15 | STP - Feed Pumps
16 | WTP -Hydropneumatic pumps - 4 Nos
17 | Jockey Pumps - 14 Nos
18 | Podium Hydrants
19 | WTP -Treated Water Sump -2 Nos
20 | STP- Final Tank
21 | Garden area chambers
Remarks:

## Master
Aparna Property Management Services Pvt Ltd
Planned Preventive Maintenance Schedule forthe year - 2018
Categeory | Job Description | PM Frequency | Remarks | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Electrical | Transformers - 4 Nos | Annually | Before Monsoon | bar: May 19; November 45
| 33 KV VCB & CTPT Panels - 13 Nos | Annually | Before Monsoon | bar: May 19; December 49
| LT Panels - ACB's - 4 Nos | Annually | Before Monsoon | bar: May 19
| DG Sets - 250 KVA - 16 Nos | Monthly(AMC) | bar: January 2; February 7; March 11; April 16; May 20; June 25; July 29; August 33; September 37; October 41; November 46; December 50
| Main PCC Panels - 8 Nos | Annually
| Earth Pits | Half yearly | Garden cutting will be done in march Month, so work should be done at that time | bar: March 14; November 45
| CC Cameras - 40 Nos | Quarterly | bar: March 11; June 25; October 41; December 52
| Boom Barriers - 8 Nos | Quarterly | bar: March 10; June 24; October 40; December 51
| Solar Fencing | Monthly(AMC) | Security wise, it is important for that month maintenace will be done | bar: January 5; February 9; March 14; April 18; May 23; June 27; July 31; August 35; September 39; October 44; November 48; December 52
| Sub cellar Ventillation System | Annually | bar: June 24
| Lightning Arrestor -7 Nos | Annually | bar: March 14
| Club House Panel - 2 Nos | Half yearly | bar: February 7; August 33
| Fire Panels - 14 Nos | Annually | bar: May 23
| STP Panel - 2 Nos | Quarterly | bar: March 14; June 27; September 39; December 52
| WTP Panel - 1 No | Quarterly | bar: March 10; June 24; September 36; December 49
| Common Supply Panels - 7 Nos | Half yearly | bar: March 11; June 25; September 37; December 50
| Land Scape Lighting panels -7 Nos | Half yearly | bar: March 14; October 40
| Irrigation starters - 14 Nos | Half yearly | bar: June 24; December 49
| Water Body Starters | Half yearly | bar: March 10; June 24; September 36; December 49
| Storm Water Staters- 12 Nos | Half yearly | bar: February 9; August 35
| Borewells Starters - 9 Nos | Quarterly | bar: March 10; June 24; September 36; December 49
STP | STP -Hydropneumatic pumps - 4 Nos | Monthly(AMC) | bar: January 5; February 9; March 14; April 18; May 23; June 27; July 31; August 35; September 39; October 44; November 48; December 52
| STP- Air Blowers - 3 Nos | Half yearly | bar: June 25; December 50
| STP- Filter feed pumps - 2 Nos | Quarterly | bar: January 2; April 16; July 29; October 41
| STP- Raw sewage pumps - 2 Nos | Half yearly | bar: April 16; October 41
| STP - Sludge Transfer Pumps - 2 Nos | Quarterly | bar: January 2; April 16; July 29; October 41
| STP - Feed Pumps | Half Yearly | bar: June 24; December 49
| STP- Filters - 4 Nos | Half yearly | bar: January 2
| STP- De-watering pump - 1 Nos | Half yearly | bar: April 18; October 41
| STP- AHU | Half yearly | bar: April 18; October 41
| STP- Centrifuge | Half yearly | bar: April 15; October 40
WTP | WTP -Hydropneumatic pumps - 4 Nos | Monthly(AMC) | bar: January 5; February 9; March 14; April 18; May 23; June 27; July 31; August 35; September 39; October 44; November 48; December 52
| WTP - Filters - 2 Nos | Annually | bar: April 15
| WTP - Filter feed pumps - 3 Nos | Half Yearly | bar: February 6; August 33; November 46
| WTP - Rain Water Pump -1 Nos | Annually | bar: February 7
| WTP - De-Watering Pump - 1 Nos | Half Yearly | bar: February 6; August 33; November 46
Fire & safety | Jockey Pumps - 14 Nos | Monthly(AMC) | bar: January 5; February 9; March 14; April 18; May 23; June 27; July 31; August 35; September 39; October 44; November 48; December 52
| Main Pumps - 14 Nos | Anually | bar: June 25
| DG Engine Pumps - 14 Nos | Monthly(AMC) | bar: May 20; November 46
| Fire Alarms & PA System | Quaterly | bar: February 9; May 23; August 35
Sumps & Tanks Cleaning | WTP -Raw Water Sump - 2 Nos | Quarterly | bar: February 8; May 22; August 34; November 47
| WTP -Treated Water Sump -2 Nos | Quarterly | bar: March 10; June 24; September 36; December 49
| STP - Pre-filtration tank | Alternate Months
| STP- Final Tank | As Require
| Rain Water Sump -1 nos | Annually | Before Monsoon | bar: April 18
| Storm Water Sump - 12 Nos | Annually | Before Monsoon | bar: April 18
| Fire Sumps -14 Nos | Annually | In rainy Season there is no need of water(June-July) | bar: June 25 to July 29
Plumbing | Irrigation sprinkler system | Half yearly | bar: May 23; November 48
| Garden area chambers | Half yearly | Garden cutting will be done in march Month, so work should be done at that time | bar: June 24; December 49
| PRV 's | Annually | bar: April 18
| Water Body Pumps | Half yearly | bar: March 14; September 39
| Storm Water Pumps - 12 Nos | Half yearly | bar: April 15; October 40

## Sheet3 (hidden)
Planned Preventive Maintenance for Month of October
Sl No | Job Description | PM Frequency
1 | DG Sets - 250 KVA - 16 Nos | AMC
2 | Solar Fencing | AMC
3 | STP -Hydropneumatic pumps - 4 Nos | AMC
4 | STP- Filter feed pumps - 4 Nos
5 | STP- Raw sewage pumps - 2 Nos
6 | STP - Sludge Transfer Pumps - 2 Nos
7 | STP- De-watering pump - 1 Nos
8 | STP- AHU
9 | STP- Centrifuge
10 | WTP -Hydropneumatic pumps - 4 Nos | AMC
11 | Jockey Pumps - 14 Nos
12 | Podium Hydrants
13 | Mist Fountain Pumps
Remarks: